## Review
200V migration: items for review
Set a Decision for each item and add comments. Item details are on the other tabs.
# | Section | Switch | Port | Item | Evidence | Proposed action | Decision | Comments
1. Device list: ports filled in by script
1 | 1 | switch-200V-LT2-1 | 1/1/6 | AV: PDU (master row 1068) | Master list lookup failed (N/A). MAC B8-80-4F-28-58-24 found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
2 | 1 | switch-200V-LT2-1 | 1/1/7 | AV: Recorder (master row 1215) | Master list lookup failed (N/A). MAC 00-1C-08-00-6C-7C found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
3 | 1 | switch-200V-LT2-1 | 1/1/8 | AV: Audio DSP (master row 759) | Master list lookup failed (N/A). MAC 78-45-01-0C-7D-3A found on this port in the 200V tab (1230 (200V_av)). Also confirmed by LLDP on 6 Oct | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
4 | 1 | switch-200V-LT2-1 | 1/1/10 | AV: LCD 2 (master row 910) | Master list lookup failed (N/A). MAC A8-4A-63-30-73-66 found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
5 | 1 | switch-200V-LT2-1 | 1/1/11 | AV: LCD 1 (master row 909) | Master list lookup failed (N/A). MAC A8-4A-63-30-73-67 found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
6 | 1 | switch-200V-LT2-1 | 1/1/12 | AV: PTZ Camera (master row 1204) | Master list lookup failed (N/A). MAC DC-E2-AC-02-E4-F5 found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
7 | 1 | switch-200V-LT2-1 | 1/1/13 | AV: Room Camera (master row 1253) | Master list lookup failed (N/A). MAC B8-A4-4F-69-B2-72 found on this port in the 200V tab (1230 (200V_av)). Also confirmed by LLDP on 6 Oct | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
8 | 1 | switch-200V-LT2-1 | 1/1/14 | AV: Occupancy Sensor (master row 957) | Master list lookup failed (N/A). MAC B8-98-B0-0F-1C-66 found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
9 | 1 | switch-200V-LT2-1 | 1/1/15 | AV: Projector Screen 2 (master row 1195) | Master list lookup failed (N/A). MAC 04-91-62-D7-70-0D found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover; device not yet seen on 2700 (AV team check, item 99)
10 | 1 | switch-200V-LT2-1 | 1/1/16 | AV: Projector Screen 1 (master row 1194) | Master list lookup failed (N/A). MAC 54-10-EC-A2-E8-27 found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover; device not yet seen on 2700 (AV team check, item 100)
11 | 1 | switch-200V-LT2-1 | 1/1/17 | AV: Projector 1 (master row 1176) | Master list lookup failed (N/A). MAC 38-1A-52-B1-75-B6 found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) |  | Moved to 2700 in the 9 Oct cutover; no decision recorded on the Review tab before the cutover
12 | 1 | switch-200V-LT2-1 | 1/1/18 | AV: Projector 2 (master row 1180) | Master list lookup failed (N/A). MAC 38-1A-52-B1-74-BA found on this port in the 200V tab (1230 (200V_av)) | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
13 | 1 | switch-200V-LT2-1 | 1/1/20 | AV: Touch Panel (master row 1339) | Master list lookup failed (N/A). MAC C4-42-68-26-D6-48 found on this port in the 200V tab (1230 (200V_av)). Also confirmed by LLDP on 6 Oct | Accept port; move 1230 (200V_av) -> 2700 (VL-av-01) | Approve | Moved to 2700 in the 9 Oct cutover
14 | 1 | switch-200V-stack-lv6 | 4/1/24 | PhysicalAccess: cloe-000-200v (master row 1686) | Master list lookup failed (N/A). MAC 00:11:B9:08:2B:67 found on this port in the 200V tab (1213 (200V_building)) | Accept port; move 1213 (200V_building) -> 2510 (VL-bac-01) | Approve | Moved to 2510 in the 9 Oct cutover
2. Devices not found on any switch
15 | 2 |  |  | AP: r650-39-4d-10 (master row 475), MAC C8:A6:08:39:4D:10 | MAC not in the 200V tab | Find on site
16 | 2 | switch-200V-Tutorial-6.03 | 1/1/9 | AV Switcher (master row 769) | 200V tab has 01d.560a.dfc0 on Tutorial-6.03 1/1/9 (same MAC, leading zero lost). Port is untagged 1230. 6 Oct: core sees 001d.560a.dfc0 live on VLAN 1230 behind Tutorial-6.03 (lag 6) | Find on site
17 | 2 |  |  | AV: AV Switcher (master row 779), MAC 00-1D-56-0A-B4-AB | MAC not in the 200V tab | Find on site
18 | 2 |  |  | AV: Projector (master row 1121), MAC F8:25:51:72:A4:52 | MAC not in the 200V tab | Find on site
19 | 2 | switch-200V-8 | 1/1/6 (likely) | AV: Projector (master row 1134), MAC F8:25:51:CB:8C:94 | MAC not in the 200V tab. 6 Oct: core sees f825.51cb.8c94 on VLAN 1230 behind switch-200V-8 (lag 4). 1/1/6 is the only port untagged in 1230 on that switch | Find on site
20 | 2 |  |  | AV: Projector (master row 1145), MAC F8:25:51:CC:0F:C6 | MAC not in the 200V tab | Find on site
3. Ports with a device seen but none listed
21 | 3 | switch-200V-LT2-1 | 1/1/9 | Unlisted device | MAC 00:50:56:05:43:F1 seen in 200V tab; port untagged 1230 (200V_av). 00:50:56 is a VMware virtual MAC | Identify device
22 | 3 | switch-200V-LT2-1 | 1/1/21 | Unlisted device | MAC 48:21:0B:56:AC:A4 seen in 200V tab; port untagged 1240 (200V_staff). LLDP: CLA-TAN3130059J (NUC, MAC 48:21:0B:56:AC:A4), not in device list | Identify device
23 | 3 | switch-200V-LT2-3 | 1/1/4 | Unlisted device | MAC d4:a2:cd:e1:dd:0e seen in 200V tab; port untagged 1240 (200v_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down (nothing connected on LT2-3)
24 | 3 | switch-200V-Tutorial-6.03 | 1/1/3 | Unlisted device | MAC F8:25:51:CB:8C:76 seen in 200V tab; port untagged 1230 | Identify device
25 | 3 | switch-200V-stack-lv3 | 1/1/48 | Unlisted device | MAC 00:09:F5:32:DB:49 seen in 200V tab; port untagged 100 (management) | Identify device |  | 2000 10.21.0.0/24 VL-netmgmt-01 ¦ NOT moved: left on 100. Device live (0009.f532.db49); addressing unknown. Confirm DHCP or re-address into 10.21.0.0/24 before moving to 2000
26 | 3 | switch-200V-stack-lv3 | 2/1/16 | Unlisted device | MAC D8:43:AE:B1:69:BE seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
27 | 3 | switch-200V-stack-lv3 | 2/1/29 | Unlisted device | MAC D8:43:AE:B1:6E:9B seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
28 | 3 | switch-200V-stack-lv3 | 3/1/5 | Unlisted device | MAC 4C:C5:D9:D0:8D:2A seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down
29 | 3 | switch-200V-stack-lv3 | 3/1/29 | Unlisted device | MAC D8:3A:DD:C6:37:A8 seen in 200V tab; port untagged 230 (Library) | Identify device | Done | 2530(vl-library-01) ¦ Moved 9 Oct; MAC learned on 2530
30 | 3 | switch-200V-stack-lv3 | 3/1/31 | Unlisted device | MAC D0:C1:B5:21:B3:20 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down
31 | 3 | switch-200V-stack-lv3 | 3/1/33 | Unlisted device | MAC 1C:1A:DF:C2:45:23 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link up, no MAC yet (device idle, 0 packets in)
32 | 3 | switch-200V-stack-lv3 | 3/1/43 | Unlisted device | MAC 1C:1A:DF:C2:45:39 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link up, no MAC yet (device idle)
33 | 3 | switch-200V-stack-lv3 | 4/1/28 | Unlisted device | MAC AC:B4:80:F1:61:85 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down
34 | 3 | switch-200V-stack-lv3 | 4/1/29 | Unlisted device | MAC 2C:CF:67:A6:4B:DE seen in 200V tab; port untagged 230 (Library) | Identify device | Done | 2530(vl-library-01) ¦ Moved 9 Oct; MAC learned on 2530
35 | 3 | switch-200V-stack-lv3 | 4/1/41 | Unlisted device | MAC D8:43:AE:B1:6C:A8 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
36 | 3 | switch-200V-stack-lv3 | 4/1/46 | Unlisted device | MAC D8:43:AE:B1:6D:30 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
37 | 3 | switch-200V-stack-lv3 | 5/1/18 | Unlisted device | MAC D8:43:AE:B1:6E:B0 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
38 | 3 | switch-200V-stack-lv3 | 5/1/24 | Unlisted device | MAC D8:43:AE:B1:6E:3C seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
39 | 3 | switch-200V-stack-lv3 | 5/1/26 | Unlisted device | MAC D8:43:AE:B1:6F:04 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
40 | 3 | switch-200V-stack-lv3 | 5/1/45 | Unlisted device | MAC D8:43:AE:B1:6F:00 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
41 | 3 | switch-200V-stack-lv4 | 1/1/14 | Unlisted device | MAC D8:43:AE:B1:6E:06 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
42 | 3 | switch-200V-stack-lv4 | 1/1/28 | Unlisted device | MAC D8:43:AE:B1:6A:29 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
43 | 3 | switch-200V-stack-lv4 | 1/1/48 | Unlisted device | MAC 00:09:F5:32:D9:F7 seen in 200V tab; port untagged 100 (management) | Identify device |  | 2000 10.21.0.0/24 VL-netmgmt-01 ¦ NOT moved: left on 100. Same vendor (00:09:F5) as lv3 1/1/48; confirm addressing before moving to 2000
44 | 3 | switch-200V-stack-lv4 | 2/1/21 | Unlisted device | MAC D8:43:AE:B1:70:1E seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
45 | 3 | switch-200V-stack-lv4 | 3/1/7 | Unlisted device | MAC D4:A2:CD:E4:99:ED seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down
46 | 3 | switch-200V-stack-lv4 | 3/1/28 | Unlisted device | MAC A0:4A:5E:E7:D5:71 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down
47 | 3 | switch-200V-stack-lv4 | 4/1/6 | Unlisted device | MAC D8:43:AE:B1:6D:56 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
48 | 3 | switch-200V-stack-lv4 | 4/1/19 | Unlisted device | MAC 38:4B:76:E0:B0:B1 seen in 200V tab; port untagged 1272 (200V_av). Same vendor prefix (38:4B:76) as the listed Airtames | Identify device | Done | Airtame-type device (384b.76e0.b0b1); moved 1272 -> 2700 on 10 Oct
49 | 3 | switch-200V-stack-lv4 | 4/1/30 | Unlisted device | MAC F8:25:51:CC:2C:76 seen in 200V tab; port untagged 1230 (200V_av) | Identify device | Done | Moved 1230 -> 2700 on 10 Oct (confirmed Pvid 2700 in show interfaces brief)
50 | 3 | switch-200V-stack-lv4 | 5/1/7 | Unlisted device | MAC D8:43:AE:B1:69:32 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
51 | 3 | switch-200V-stack-lv4 | 5/1/12 | Unlisted device | MAC D8:43:AE:B1:6C:8C seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
52 | 3 | switch-200V-stack-lv4 | 5/1/21 | Unlisted device | MAC D8:43:AE:B1:6D:DF seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
53 | 3 | switch-200V-stack-lv4 | 5/1/29 | Unlisted device | MAC D8:43:AE:B1:6F:10 seen in 200V tab; port untagged 1230 (200V_av) | Move 1230 -> 2700 with the rest of the room AV (config in 200V-av-unlisted-2700-ICX.txt) | Done | Moved 1230 -> 2700 on 9 Oct (200V-av-unlisted-2700-ICX.txt)
54 | 3 | switch-200V-stack-lv6 | 1/1/31 | Unlisted device | MAC 1C:1A:DF:C2:44:7A seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link up (1272/1273 still tagged), MAC not yet checked
55 | 3 | switch-200V-stack-lv6 | 3/1/1 | Unlisted device | MAC A0:4A:5E:E7:D3:D5 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down
56 | 3 | switch-200V-stack-lv6 | 4/1/1 | Unlisted device | MAC 1C:1A:DF:C2:45:96 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link up, no MAC yet (device idle)
57 | 3 | switch-200V-stack-lv6 | 5/1/30 | Unlisted device | MAC 1C:1A:DF:C0:98:B8 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; MAC learned on 2100
58 | 3 | switch-200V-stack-lv6 | 5/1/48 | Unlisted device | MAC 1C:1A:DF:C2:4E:3C seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link up, no MAC yet (device idle)
59 | 3 | switch-200V-stack-lv6 | 6/1/16 | Unlisted device | MAC 1C:1A:DF:C0:31:0F seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; MAC learned on 2100
60 | 3 | switch-200V-stack-lv6 | 6/1/22 | Unlisted device | MAC 1C:1A:DF:C2:51:31 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; link down
61 | 3 | switch-200V-stack-lv6 | 6/1/31 | Unlisted device | MAC 48:21:0B:56:AE:44 seen in 200V tab; port untagged 1240 (200V_staff) | Identify device | Done | VL-staff-wired-01 - 2100 ¦ Moved 9 Oct; MAC learned on 2100
62 | 3 | switch-200V-8 | 1240 port | Unlisted device | 6 Oct: core sees 0009.f532.db14 and 0009.f532.db15 on VLAN 1240 behind switch-200V-8 (lag 4). Port not known; 1240 is untagged on 1/1/1-1/1/5 and 1/1/7-1/1/11. Same vendor prefix (00:09:F5) as the unlisted devices on lv3 and lv4 1/1/48 | Identify device
4. Ports needing a decision (no device seen)
63 | 4 | switch-200V-stack-lv6 | 2/1/47 | Already untagged on 2010, no AP listed | Port is on a new VLAN outside the pilot | Confirm on site |  | GC - leave the VLAN as they are
64 | 4 | switch-200V-stack-lv4 | 2/1/8 | Untagged on 1212 (CCTV), no camera listed | No MAC seen | Confirm on site |  | GC - leave the VLAN as they are
65 | 4 | switch-200V-stack-lv3 | 1/1/12 | AP-style port with no AP listed | Untagged 100 with tagged VLANs on top (AP-style port); no AP listed, no MAC seen | Confirm on site |  | GC - leave the VLAN as they are
66 | 4 | switch-200V-stack-lv4 | 1/1/8 | AP-style port with no AP listed | Untagged 100 with tagged VLANs on top (AP-style port); no AP listed, no MAC seen | Confirm on site |  | GC - leave the VLAN as they are
67 | 4 | switch-200V-stack-lv6 | 1/1/35 | AP-style port with no AP listed | Untagged 100 with tagged VLANs on top (AP-style port); no AP listed, no MAC seen | Confirm on site |  | GC - leave the VLAN as they are
68 | 4 | switch-200V-stack-lv6 | 5/1/35 | AP-style port with no AP listed | Untagged 100 with tagged VLANs on top (AP-style port); no AP listed, no MAC seen | Confirm on site |  | GC - leave the VLAN as they are
69 | 4 | switch-200V-LT2-1 | 1/1/2 | AP-style port with no AP listed | Untagged 100 with tagged VLANs on top (AP-style port); no AP listed, no MAC seen. PoE disabled (no inline power) | Confirm on site |  | GC - leave the VLAN as they are
70 | 4 | switch-200V-Tutorial-6.03 | 1/1/11 | Untagged 100, no tagged VLANs, no device | No MAC seen | Confirm on site |  | GC - leave the VLAN as they are
71 | 4 | switch-200V-stack-lv3 | 3/1/28 | Untagged 230 (Library), no device | No MAC seen; VLAN 230 not in the 200V mapping | Confirm on site |  | GC - leave the VLAN as they are
72 | 4 |  |  | Default for 1240 ports with no device: 2100 | 222 ports on 1240 have no device listed. In the pilot 1240 went to 2100 (outlets), 2800 (printers) or 2700 (NUC) | Confirm on site |  | GC - leave the VLAN as they are
5. Trunk ports to identify before cutover
73 | 5 | switch-200V-stack-lv6 | 1/1/3 | Tagged-only port, nothing connected | Checked 6 Oct: untagged VLAN 1 (PVID 1), link down, no LLDP neighbour, no MACs learned, PoE on, drawing 0 W. Carries old VLANs only | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
74 | 5 | switch-200V-stack-lv6 | 1/1/6 | Tagged-only port, nothing connected | Checked 6 Oct: untagged VLAN 1 (PVID 1), link down, no LLDP neighbour, no MACs learned, PoE on, drawing 0 W. Carries old VLANs only | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
75 | 5 | switch-200V-stack-lv6 | 2/1/46 | Tagged-only port, nothing connected | Checked 6 Oct: untagged VLAN 1 (PVID 1), link down, no LLDP neighbour, no MACs learned, PoE on, drawing 0 W. Carries old VLANs only | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
76 | 5 | switch-200V-stack-lv6 | 7/1/1 | Tagged-only port, nothing connected | Checked 6 Oct: untagged VLAN 1 (PVID 1), link down, no LLDP neighbour, no MACs learned, unit 7 has no PoE. Carries old VLANs only | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
77 | 5 | switch-200V-Tutorial-6.03 | 1/1/1 | Tagged-only port, nothing connected | 6 Oct: all 8 MACs the core sees behind Tutorial-6.03 (lag 6) are known devices on other ports, so nothing is behind this port. No remote login to the switch to confirm | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
78 | 5 | switch-200V-Tutorial-6.03 | 1/1/10 | Tagged-only port, nothing connected | 6 Oct: all 8 MACs the core sees behind Tutorial-6.03 (lag 6) are known devices on other ports, so nothing is behind this port. No remote login to the switch to confirm | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
79 | 5 | switch-200V-Tutorial-6.03 | 1/1/12 | Tagged-only port, nothing connected | 6 Oct: all 8 MACs the core sees behind Tutorial-6.03 (lag 6) are known devices on other ports, so nothing is behind this port. No remote login to the switch to confirm | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
80 | 5 | switch-200V-8 | 1/1/12 | Tagged-only port, most likely nothing connected | 6 Oct: behind switch-200V-8 (lag 4) the core sees only the switch itself, a projector on 1230 and one device on 1240; no other MACs that would point to something on this port. No remote login to confirm | Leave as is; no cutover action. Remove old VLANs when they are retired |  | 9 Oct: left as is
6. Switch config points
81 | 6 | trinity200V-core |  | Set system-max spanning-tree 40 | 34 VLANs, spanning-tree on 32. Current limit: default (32). VLANs without spanning-tree: 2952, 2953. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
82 | 6 | switch-200V-stack-lv3 |  | Set system-max spanning-tree 40 | 35 VLANs, spanning-tree on 32. Current limit: default (32). VLANs without spanning-tree: 2311, 2321, 2953. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
83 | 6 | switch-200V-stack-lv4 |  | Reload to apply system-max spanning-tree 40 | 35 VLANs, spanning-tree on 32. Current limit: 40 configured, not yet active. VLANs without spanning-tree: 2311, 2321, 2953. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt 40 is already saved; reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
84 | 6 | switch-200V-stack-lv6 |  | Set system-max spanning-tree 40, then enable spanning-tree on 2600 and 2700 | 35 VLANs, spanning-tree on 32. Current limit: default (32). VLANs without spanning-tree: 2600, 2700, 2953. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window, then: configure terminal vlan 2600 spanning-tree exit vlan 2700 spanning-tree exit write memory |  | Done 9 Oct: reloaded, spanning-tree current 40; STP on 2600 and 2700 enabled
85 | 6 | switch-200V-LT2-1 |  | Set system-max spanning-tree 40 | 34 VLANs, spanning-tree on 32. Current limit: default (32). VLANs without spanning-tree: 2311, 2321. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
86 | 6 | switch-200V-LT2-2 |  | Set system-max spanning-tree 40 | 32 VLANs, spanning-tree on 32. Current limit: default (32). VLANs without spanning-tree: none. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
87 | 6 | switch-200V-LT2-3 |  | Set system-max spanning-tree 40 | 32 VLANs, spanning-tree on 32. Current limit: default (32). VLANs without spanning-tree: none. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
88 | 6 | switch-200V-8 |  | Set system-max spanning-tree 40 | 28 VLANs, spanning-tree on 28. Current limit: default (32). VLANs without spanning-tree: none. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
89 | 6 | switch-200V-Tutorial-6.03 |  | Set system-max spanning-tree 40 | 26 VLANs, spanning-tree on 26. Current limit: default (32). VLANs without spanning-tree: none. The ICX default is 32 spanning-tree instances; the new limit applies after a reload | See system-max-spanning-tree-40-ICX.txt configure terminal system-max spanning-tree 40 write memory Then reload in a maintenance window |  | Done 9 Oct: reloaded, spanning-tree current 40
90 | 6 | switch-200V-LT2-3 |  | VLAN 100 tagged on every port (1/1/1-1/1/12) | Access ports 1/1/1-11 are untagged 1240; other switches only tag 100 on uplinks/APs | Review; remove from access ports if not needed
7. Follow-ups from the 9 Oct cutover
91 | 7 | trinity200V-core |  | Unplanned change: WIFIMGMT-IN ACL (SmartZone and RADIUS) | APs on VLAN 2010 kept flapping in SmartZone: WIFIMGMT-IN denied the SmartZone private IPs. Added sequence 23 permit ip 10.21.1.0 0.0.0.255 host 192.168.81.100 and sequence 24 permit ip 10.21.1.0 0.0.0.255 host 192.168.245.100; APs stable after. Later: Trinity Wireless clients could not authenticate; the WLAN's AAA server (FreeRADIUS 10.128.131.7, UDP 18200, not proxied) was denied by seq 30. Added sequence 25 permit udp 10.21.1.0 0.0.0.255 host 10.128.131.7. Two example entries for 10.20.16.10 were pasted in error and removed | Record in the change record. Confirm write memory on the core | Done | Done 9 Oct; core saved. Recorded in the change document
92 | 7 | switch-200V-stack-lv6 |  | Unit 3 hangs; units 3 and 4 drop out of the stack | Log: units 3 and 4 deleted 20:03 on 9 Oct (rejoined 20:44 after restart) and again 22:44:19 on 9 Oct, no stack-port, power or temperature message before it. Out ~15 h until unit 3 power cycled 13:35 on 10 Oct; unit 3 uptime 5 min, unit 4 20 h. Unit 3 = ICX8200-48PF2 FNM4319U09A, 10.0.10g_cd3 | Open Ruckus TAC case and RMA unit 3 (show logging, show tech-support, show version). Until replaced: check show stack; power cycle unit 3 if units 3/4 missing
93 | 7 | switch-200V-stack-lv6 (urgent), switch-200V-stack-lv4 |  | Stack cabled as a chain, not a ring | A single stack link or unit failure splits the stack. lv3 is a ring | lv6: stack unit 4 stack-port 4/2/1 4/2/3; stack unit 7 stack-port 7/2/1 7/2/3; cable 4/2/3 to 7/2/3 out of hours. Keep unit IDs and priorities (1 active 128, 2 standby 110). lv4 later
94 | 7 | All 200V switches |  | Spanning-tree root is switch-200V-8 | switch-200V-8 has the lowest MAC, so it is root for the 802.1D VLANs. This was the case before the migration | Set a lower spanning-tree priority on trinity200V-core in a later window
95 | 7 | switch-200V-stack-lv6 |  | Check STP on VLAN 2600 | lg10 on 2700 confirmed FORWARDING; 2600 not yet checked | show span vlan 2600: lg10 FORWARDING
96 | 7 | switch-200V-stack-lv4, switch-200V-Tutorial-6.03, trinity200V-core |  | Confirm write memory | write memory confirmed on lv6 and lv3 (9 Oct, after the Review tab changes) and LT2-3 | Run write memory on each and confirm
97 | 7 | switch-200V-stack-lv6 | 7/1/19 | Printer 200v-lvl-6-staff-corridor | Ended up on 2700 during the paste; moved to 2800 the same night | Test print on Saturday
98 | 7 | switch-200V-Tutorial-6.03 | 1/1/3, 1/1/9 | Two extra ports moved to 2700 | Both were on 1230 with a MAC seen but no device listed. 1/1/9 is the AV Switcher on the Not found tab (master row 769); 1/1/3 is F8:25:51:CB:8C:76 | Add both devices to the master list
99 | 7 | switch-200V-LT2-1 | 1/1/15 | AV not yet seen on 2700: Projector Screen 2 (04-91-62-D7-70-0D) | Port moved; no MAC learned on the port after the cutover. Probably idle or powered off | AV team to check on Saturday
100 | 7 | switch-200V-LT2-1 | 1/1/16 | AV not yet seen on 2700: Projector Screen 1 (54-10-EC-A2-E8-27) | Port moved; no MAC learned on the port after the cutover. Probably idle or powered off | AV team to check on Saturday
101 | 7 | switch-200V-stack-lv4 | 4/1/41 | AV not yet seen on 2700: Projector Screen Left (80:34:28:5C:F1:F2) | Port moved; no MAC learned on the port after the cutover. Probably idle or powered off | AV team to check on Saturday
102 | 7 | switch-200V-stack-lv4 | 5/1/37 | AV not yet seen on 2700: Projector Right (38:1A:52:B2:00:9F) | Port moved; no MAC learned on the port after the cutover. Probably idle or powered off | AV team to check on Saturday
103 | 7 | switch-200V-stack-lv4 | 5/1/39 | AV not yet seen on 2700: Projector Left (38:1A:52:B1:FF:B9) | Port moved; no MAC learned on the port after the cutover. Probably idle or powered off | AV team to check on Saturday
104 | 7 | switch-200V-Tutorial-6.03 | 1/1/8 | AV not yet seen on 2700: PDU (B8:80:4F:28:58:2D) | Port moved; 7 of 8 devices seen on 2700, this one not | AV team to check on Saturday
105 | 7 | SmartZone |  | Trinity Wireless v2300: clients authenticate but get no IP | 200v WLAN group overrides are all Default, so the WLAN maps to VLAN 2300 as built | Find the client MAC on the core (show mac-address); check ve 2300 helpers, STUDENT-GROUP-IN, DHCP snooping and the 10.21.8.0/21 scope
106 | 7 | SmartZone |  | Trinity NetSegPilot is not in the 200v WLAN group | The plan was to keep NetSegPilot (VLAN 2300); the group now holds eduroam v2900, Trinity Visitor v2900 and Trinity Wireless v2300 | Confirm whether it was removed on purpose; add back if not
107 | 7 | SmartZone |  | Trinity Wireless v2300: no IP, then authentication failure | WLAN group overrides all Default (VLAN 2300). Authentication failed because WIFIMGMT-IN denied the APs' RADIUS requests to 10.128.131.7; fixed with sequence 25. Path checked with ping/traceroute from 10.21.1.1. Trinity Wireless working 9 Oct | Confirm clients get 10.21.8.x. Confirm whether Trinity also changed FreeRADIUS clients.conf or the firewall at 10.136.0.2 for 10.21.1.0/24 | Done | Working 9 Oct
108 | 7 | switch-200V-stack-lv3, switch-200V-stack-lv6 | 3/1/33, 3/1/43; 1/1/31, 4/1/1, 5/1/48 | Review tab ports with link up but no MAC on 2100 | Moved 9 Oct; link up but no MAC learned yet (lv3 3/1/33 showed 0 packets in). Most likely idle devices | show mac-address vlan 2100 on lv3 and lv6 on Saturday
109 | 7 | switch-200V-stack-lv3, switch-200V-stack-lv4 | 1/1/48 | 00:09:F5 devices left on VLAN 100 (Review items 25, 43) | Live on VLAN 100 (lv3 0009.f532.db49). Not known whether they have a fixed 192.168.122.x address | Confirm addressing; then move to 2000 with the lines in 200V-review-changes-ICX.txt
110 | 7 | SmartZone |  | Test eduroam v2900 and Trinity Visitor v2900 | Both should give 10.21.29.x. eduroam's RADIUS server may be outside the ranges WIFIMGMT-IN permits | Test both; if eduroam fails, get its RADIUS server IP and add a WIFIMGMT-IN entry before sequence 30
111 | 7 | switch-200V-stack-lv3, switch-200V-stack-lv4 | lv3 2/1/26; lv4 1/1/24, 2/1/24 | Patching sheet and device list disagree | Dycom patching sheet (2025-07-30) puts outlets 200V3J14, 200V4I17 and 200V4H9 (20:7B:D2:30 devices C1, 99:25, 99:15) on these ports; the device list has a Touch Panel and two Airtames there. Ports are on 2700 | Confirm on site what is patched; if the 20:7B:D2:30 devices are there, move the ports to 2100
112 | 7 | switch-200V-stack-lv6 |  | SmartZone shows 5 stack members instead of 7 | Switch Online in SmartZone; show stack on the switch has all 7 units Ready after 13:35 on 10 Oct. manager disable / no manager disable and write memory did not refresh it | Display issue only. Add to the TAC case; do not delete/re-add the switch or reload the stack for it. Use show stack on the switch meanwhile

## Old VLAN ports 10 Oct
Ports still untagged on an old VLAN, from show interfaces brief on 10 Oct 2026 (lv3, lv4, lv6; lv6 1240 ports re-checked after units 3 and 4 rejoined). Pvid 1, uplinks and stack ports are left out.
Switch | Port | Link | Speed | Tagged | Old VLAN | Suggested new VLAN | Review item | Notes | MAC seen 10 Oct
lv3 | 1/1/12 | Down |  | Yes | 100 (management) | AP-style port (tagged VLANs) | 65
lv3 | 1/1/34 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 1/1/48 | Up | 100M | No | 100 (management) | 2000 (VL-netmgmt-01) once addressing is confirmed | 25, 109 | MAC seen 6 Oct: 00:09:F5:32:DB:49 | 0009.f532.db49
lv3 | 2/1/14 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 2/1/24 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01) | 111
lv3 | 2/1/27 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 2/1/34 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 3/1/3 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/7 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/10 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/11 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/13 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/15 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/16 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/19 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/20 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | Moved to 2100 on 10 Oct. | 1c1a.dfc2.5143
lv3 | 3/1/27 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 3/1/28 | Down |  | No | 230 (Library) | 2530 (VL-library-01) - check | 71
lv3 | 4/1/2 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 4/1/23 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 4/1/24 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 4/1/25 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 4/1/26 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 4/1/27 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv3 | 4/1/45 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/4 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/5 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/6 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/7 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/13 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/15 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/20 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/32 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv3 | 5/1/43 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 1/1/8 | Down |  | Yes | 100 (management) | AP-style port (tagged VLANs) | 66
lv4 | 1/1/17 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 1/1/32 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 1/1/48 | Up | 100M | No | 100 (management) | 2000 (VL-netmgmt-01) once addressing is confirmed | 43, 109 | MAC seen 6 Oct: 00:09:F5:32:D9:F7 | 0009.f532.d9f7
lv4 | 2/1/8 | Down |  | No | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | 64
lv4 | 2/1/18 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 2/1/20 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 3/1/1 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | Moved to 2100 on 10 Oct. | 1c1a.dfc2.4cc3
lv4 | 3/1/4 | Up | 10M | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/5 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/9 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/11 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/13 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/14 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/19 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/20 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/21 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/22 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/27 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/29 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/30 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/35 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/37 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/39 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/42 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/43 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/45 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/47 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 3/1/48 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv4 | 4/1/1 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/2 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/7 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/10 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/16 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/17 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/19 | Up | 1G | No | 1272 (200V_av) | 2700 (VL-av-01) | 48 | Moved to 2700 on 10 Oct. MAC seen 6 Oct: 38:4B:76:E0:B0:B1 | 384b.76e0.b0b1
lv4 | 4/1/27 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/28 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/29 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/31 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/32 | Down |  | No | 1272 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/38 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/39 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 4/1/44 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/1 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/2 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/5 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/14 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/16 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/19 | Down |  | No | 1272 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/24 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/26 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/35 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/38 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/40 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/43 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv4 | 5/1/47 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 1/1/1 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/2 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/4 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/5 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/7 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/11 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/12 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/30 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/32 | Up | 1G | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/33 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/34 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/35 | Down |  | Yes | 100 (management) | AP-style port (tagged VLANs) | 67
lv6 | 1/1/36 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/41 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/42 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/43 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/44 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/45 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/46 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/47 | Down |  | Yes | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 1/1/48 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/4 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/5 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/6 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/7 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/8 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/9 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/10 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/11 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/12 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/13 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 2/1/48 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/2 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 3/1/3 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/4 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/5 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/6 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/7 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/8 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/9 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/10 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/21 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/22 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 3/1/23 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 4/1/2 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 4/1/3 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 4/1/7 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 4/1/9 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/2 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/3 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/4 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/5 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/6 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/7 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/8 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/9 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/10 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/11 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/12 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/13 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/14 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/15 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/16 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/17 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/18 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/19 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/20 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/21 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/22 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/23 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/24 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/25 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/26 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/27 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/28 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/29 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/31 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/32 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/33 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/35 | Down |  | Yes | 100 (management) | AP-style port (tagged VLANs) | 68
lv6 | 5/1/36 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/37 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 5/1/39 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/40 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/41 | Up | 10M | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/43 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/44 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/45 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/46 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 5/1/47 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/1 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/2 | Up | 1G | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/3 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/4 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/5 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/6 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/7 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/8 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/9 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/10 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/11 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/12 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/13 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/14 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/15 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/17 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/18 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/19 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 6/1/21 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/23 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 6/1/25 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/29 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 6/1/30 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/32 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/33 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/36 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/37 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/42 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/43 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/44 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/47 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 6/1/48 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/2 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/6 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/7 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 7/1/12 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/13 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/15 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/16 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/18 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/20 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/21 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/25 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/26 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/29 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/36 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/37 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/38 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/39 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/41 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/42 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/43 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 7/1/45 | Down |  | No | 1230 (200V_av) | 2700 (VL-av-01)
lv6 | 7/1/46 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/47 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
lv6 | 7/1/48 | Down |  | No | 1240 (200V_staff) | 2100 (VL-staff-wired-01)
Summary
lv3 | 100 (management) | 2
lv3 | 1230 (200V_av) | 15
lv3 | 1240 (200V_staff) | 16
lv3 | 230 (Library) | 1
lv4 | 100 (management) | 2
lv4 | 1212 (200V_IPcam) | 1
lv4 | 1230 (200V_av) | 29
lv4 | 1240 (200V_staff) | 22
lv4 | 1272 (200V_av) | 3
lv6 | 100 (management) | 2
lv6 | 1230 (200V_av) | 8
lv6 | 1240 (200V_staff) | 136
Total |  | 237
Light orange = link up (device connected). Dark orange = port has a device in the device list but is still on an old VLAN.

## 200V Devices
Master row | Type | Device | MAC | Switch name | Port | Old VLAN | New VLAN | Status | Port source
469 | AP | r650-39-49-a0 | C8:A6:08:39:49:A0 | switch-200V-LT2-1 | 1/1/1 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
1104 | AV | Pro convert for NDI to HDMI | D0:C8:57:81:64:24 | switch-200V-LT2-1 | 1/1/4 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
708 | AV | Airtame | 38:4b:76:f1:8f:ec | switch-200V-LT2-1 | 1/1/5 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1068 | AV | PDU | B8-80-4F-28-58-24 | switch-200V-LT2-1 | 1/1/6 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1215 | AV | Recorder | 00-1C-08-00-6C-7C | switch-200V-LT2-1 | 1/1/7 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
759 | AV | Audio DSP | 78-45-01-0C-7D-3A | switch-200V-LT2-1 | 1/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
910 | AV | LCD 2 | A8-4A-63-30-73-66 | switch-200V-LT2-1 | 1/1/10 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
909 | AV | LCD 1 | A8-4A-63-30-73-67 | switch-200V-LT2-1 | 1/1/11 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1204 | AV | PTZ Camera | DC-E2-AC-02-E4-F5 | switch-200V-LT2-1 | 1/1/12 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1253 | AV | Room Camera | B8-A4-4F-69-B2-72 | switch-200V-LT2-1 | 1/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
957 | AV | Occupancy Sensor | B8-98-B0-0F-1C-66 | switch-200V-LT2-1 | 1/1/14 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1195 | AV | Projector Screen 2 | 04-91-62-D7-70-0D | switch-200V-LT2-1 | 1/1/15 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1194 | AV | Projector Screen 1 | 54-10-EC-A2-E8-27 | switch-200V-LT2-1 | 1/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1176 | AV | Projector 1 | 38-1A-52-B1-75-B6 | switch-200V-LT2-1 | 1/1/17 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1180 | AV | Projector 2 | 38-1A-52-B1-74-BA | switch-200V-LT2-1 | 1/1/18 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1339 | AV | Touch Panel | C4-42-68-26-D6-48 | switch-200V-LT2-1 | 1/1/20 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Matched from 200V tab
1223 | AV | Room Camera | B8:A4:4F:68:F4:EE | switch-200V-Tutorial-6.03 | 1/1/2 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
940 | AV | Occupancy Sensor | B8:98:B0:0F:1C:5B | switch-200V-Tutorial-6.03 | 1/1/4 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1281 | AV | Room NUC | 48:21:0B:56:AE:3A | switch-200V-Tutorial-6.03 | 1/1/5 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1318 | AV | Touch Panel | C4:42:68:38:BB:80 | switch-200V-Tutorial-6.03 | 1/1/6 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
705 | AV | Airtame | 38:4b:76:f1:89:5a | switch-200V-Tutorial-6.03 | 1/1/7 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1064 | AV | PDU | B8:80:4F:28:58:2D | switch-200V-Tutorial-6.03 | 1/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
454 | AP | r650-19-9d-00 | C8:A6:08:19:9D:00 | switch-200V-stack-lv3 | 1/1/1 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
458 | AP | r650-19-9d-70 | C8:A6:08:19:9D:70 | switch-200V-stack-lv3 | 1/1/2 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
456 | AP | r650-19-9d-50 | C8:A6:08:19:9D:50 | switch-200V-stack-lv3 | 1/1/3 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
455 | AP | r650-19-9d-40 | C8:A6:08:19:9D:40 | switch-200V-stack-lv3 | 1/1/4 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
459 | AP | r650-19-9d-80 | C8:A6:08:19:9D:80 | switch-200V-stack-lv3 | 1/1/5 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
493 | AP | r650-3d-98-40 | 5C:83:6C:3D:98:40 | switch-200V-stack-lv3 | 1/1/6 | 100 (management) | 2010 (VL-wifimgmt-01) | Done (pilot) | Master list
463 | AP | r650-32-68-f0 | CC:1B:5A:32:68:F0 | switch-200V-stack-lv3 | 1/1/7 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
461 | AP | r650-32-61-e0 | CC:1B:5A:32:61:E0 | switch-200V-stack-lv3 | 1/1/8 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
494 | AP | r650-3d-98-50 | 5C:83:6C:3D:98:50 | switch-200V-stack-lv3 | 1/1/9 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
460 | AP | r650-19-9d-a0 | C8:A6:08:19:9D:A0 | switch-200V-stack-lv3 | 1/1/10 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
457 | AP | r650-19-9d-60 | C8:A6:08:19:9D:60 | switch-200V-stack-lv3 | 1/1/11 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
1320 | AV | Touch Panel | C4:42:68:60:C1:B6 | switch-200V-stack-lv3 | 1/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1242 | AV | Room Camera | B8:A4:4F:CB:CB:F7 | switch-200V-stack-lv3 | 1/1/14 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
971 | AV | Occupancy Sensor | C4:42:68:65:7E:7F | switch-200V-stack-lv3 | 1/1/15 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1325 | AV | Touch Panel | C4:42:68:6C:42:DC | switch-200V-stack-lv3 | 1/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1238 | AV | Room Camera | B8:A4:4F:CB:C6:FB | switch-200V-stack-lv3 | 1/1/17 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
974 | AV | Occupancy Sensor | C4:42:68:65:8E:04 | switch-200V-stack-lv3 | 1/1/18 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1327 | AV | Touch Panel | C4:42:68:6C:44:8E | switch-200V-stack-lv3 | 1/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1251 | AV | Room Camera | B8:A4:4F:CE:F4:C6 | switch-200V-stack-lv3 | 1/1/20 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
970 | AV | Occupancy Sensor | C4:42:68:65:7D:A0 | switch-200V-stack-lv3 | 1/1/21 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1329 | AV | Touch Panel | C4:42:68:6D:2B:F1 | switch-200V-stack-lv3 | 1/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1334 | AV | Touch Panel | C4:42:68:6D:C3:79 | switch-200V-stack-lv3 | 1/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
983 | AV | Occupancy Sensor | C4:42:68:65:91:9B | switch-200V-stack-lv3 | 1/1/24 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1245 | AV | Room Camera | B8:A4:4F:CE:E5:EB | switch-200V-stack-lv3 | 1/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1241 | AV | Room Camera | B8:A4:4F:CB:CA:CC | switch-200V-stack-lv3 | 1/1/26 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
986 | AV | Occupancy Sensor | C4:42:68:65:95:E7 | switch-200V-stack-lv3 | 1/1/27 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1336 | AV | Touch Panel | C4:42:68:6D:C3:9E | switch-200V-stack-lv3 | 1/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1337 | AV | Touch Panel | C4:42:68:6D:C3:AB | switch-200V-stack-lv3 | 1/1/29 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
976 | AV | Occupancy Sensor | C4:42:68:65:8F:C4 | switch-200V-stack-lv3 | 1/1/30 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1244 | AV | Room Camera | B8:A4:4F:CE:E4:99 | switch-200V-stack-lv3 | 1/1/31 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1239 | AV | Room Camera | B8:A4:4F:CB:C8:54 | switch-200V-stack-lv3 | 1/1/32 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
978 | AV | Occupancy Sensor | C4:42:68:65:91:74 | switch-200V-stack-lv3 | 1/1/33 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
890 | AV | Keypad for Room-In-Use light | C4:42:68:1C:22:3B | switch-200V-stack-lv3 | 1/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
892 | AV | Keypad for Room-In-Use light | C4:42:68:46:A3:3F | switch-200V-stack-lv3 | 1/1/36 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1458 | cctv | cam-200v-AE-D7-1B.trinity.unimelb.edu.au | 00:02:d1:ae:d7:1b | switch-200V-stack-lv3 | 2/1/1 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1459 | cctv | cam-200v-AE-D7-3A.trinity.unimelb.edu.au | 00:02:d1:ae:d7:3a | switch-200V-stack-lv3 | 2/1/2 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1447 | cctv | cam-200v-ae-d6-f4.trinity.unimelb.edu.au | 00:02:d1:ae:d6:f4 | switch-200V-stack-lv3 | 2/1/3 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1450 | cctv | cam-200v-AE-D6-F7.trinity.unimelb.edu.au | 00:02:d1:ae:d6:f7 | switch-200V-stack-lv3 | 2/1/4 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1457 | cctv | cam-200v-AE-D7-0A.trinity.unimelb.edu.au | 00:02:d1:ae:d7:0a | switch-200V-stack-lv3 | 2/1/5 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1446 | cctv | cam-200v-AE-D6-ED.trinity.unimelb.edu.au | 00:02:d1:ae:d6:ed | switch-200V-stack-lv3 | 2/1/6 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1455 | cctv | cam-200v-AE-D7-01.trinity.unimelb.edu.au | 00:02:d1:ae:d7:01 | switch-200V-stack-lv3 | 2/1/7 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1174 | AV | Projector | F8:25:51:D2:70:8E | switch-200V-stack-lv3 | 2/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1333 | AV | Touch Panel | C4:42:68:6D:BF:ED | switch-200V-stack-lv3 | 2/1/15 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
698 | AV | Airtame | 38:4B:76:F1:83:52 | switch-200V-stack-lv3 | 2/1/18 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1019 | AV | PDU | 28:B5:E8:6F:27:18 | switch-200V-stack-lv3 | 2/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
796 | AV | AV Switcher | C4:42:68:65:35:E8 | switch-200V-stack-lv3 | 2/1/20 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1236 | AV | Room Camera | B8:A4:4F:CB:C5:56 | switch-200V-stack-lv3 | 2/1/21 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
972 | AV | Occupancy Sensor | C4:42:68:65:87:C4 | switch-200V-stack-lv3 | 2/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1143 | AV | Projector | F8:25:51:CC:0F:7D | switch-200V-stack-lv3 | 2/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1024 | AV | PDU | 28:B5:E8:6F:CB:2E | switch-200V-stack-lv3 | 2/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1335 | AV | Touch Panel | C4:42:68:6D:C3:9C | switch-200V-stack-lv3 | 2/1/26 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
801 | AV | AV Switcher | C4:42:68:65:39:D8 | switch-200V-stack-lv3 | 2/1/28 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
697 | AV | Airtame | 38:4B:76:F1:83:51 | switch-200V-stack-lv3 | 2/1/30 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
902 | AV | LCD | F8:01:B4:53:86:B8 | switch-200V-stack-lv3 | 2/1/31 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
893 | AV | Keypad for Room-In-Use light | C4:42:68:59:A4:45 | switch-200V-stack-lv3 | 2/1/32 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
719 | AV | Airtame | 38:4B:76:F1:95:78 | switch-200V-stack-lv3 | 2/1/33 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1201 | AV | PTZ Camera | DC:E2:AC:02:E8:CA | switch-200V-stack-lv3 | 2/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
925 | AV | Mic Charger | 00:1B:66:3F:15:17 | switch-200V-stack-lv3 | 2/1/36 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1213 | AV | Recorder | 00:1C:08:00:70:A3 | switch-200V-stack-lv3 | 2/1/37 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1103 | AV | Pro convert for NDI to HDMI | D0:C8:57:80:9F:8E | switch-200V-stack-lv3 | 2/1/38 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
891 | AV | Keypad for Room-In-Use light | C4:42:68:46:82:ED | switch-200V-stack-lv3 | 2/1/39 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
829 | AV | Cresnet Bridge For Outside Sign | C4:42:68:5D:43:1D | switch-200V-stack-lv3 | 2/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1599 | printer | 200v-lvl3-student-corridor | DC:C2:C9:76:56:67 | switch-200V-stack-lv3 | 3/1/37 | 1240 (200V_staff) | 2800 (VL-print-01) | Done (pilot) | Master list
1598 | printer | 200v-lvl3-staffroom | 34:9F:7B:5E:9A:04 | switch-200V-stack-lv3 | 4/1/4 | 1240 (200V_staff) | 2800 (VL-print-01) | Done | Master list
793 | AV | AV Switcher | C4:42:68:65:29:8D | switch-200V-stack-lv3 | 4/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1014 | AV | PDU | 28:B5:E8:68:78:AF | switch-200V-stack-lv3 | 4/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1173 | AV | Projector | F8:25:51:D2:70:8A | switch-200V-stack-lv3 | 4/1/44 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
732 | AV | Airtame | 8C:AE:4C:D2:7C:B8 | switch-200V-stack-lv3 | 4/1/47 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1021 | AV | PDU | 28:B5:E8:6F:33:1E | switch-200V-stack-lv3 | 4/1/48 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
898 | AV | LCD | 74:C1:7E:EC:3D:90 | switch-200V-stack-lv3 | 5/1/1 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1378 | AV | UC Engine | 90:8D:6E:95:8E:ED | switch-200V-stack-lv3 | 5/1/2 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
730 | AV | Airtame | 38:4B:76:F1:AB:19 | switch-200V-stack-lv3 | 5/1/3 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
832 | AV | Display | 28:E6:A9:8D:5A:69 | switch-200V-stack-lv3 | 5/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
733 | AV | Airtame | 8C:AE:4C:D2:7C:BC | switch-200V-stack-lv3 | 5/1/9 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
806 | AV | AV Switcher | C4:42:68:65:3F:BD | switch-200V-stack-lv3 | 5/1/10 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1151 | AV | Projector | F8:25:51:CD:3F:DA | switch-200V-stack-lv3 | 5/1/12 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1166 | AV | Projector | F8:25:51:CF:D3:D8 | switch-200V-stack-lv3 | 5/1/14 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1027 | AV | PDU | 28:B5:E8:6F:CB:5E | switch-200V-stack-lv3 | 5/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
734 | AV | Airtame | 8C:AE:4C:D2:7C:D8 | switch-200V-stack-lv3 | 5/1/17 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1171 | AV | Projector | F8:25:51:D2:70:34 | switch-200V-stack-lv3 | 5/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
718 | AV | Airtame | 38:4B:76:F1:95:77 | switch-200V-stack-lv3 | 5/1/21 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1016 | AV | PDU | 28:B5:E8:68:7E:2B | switch-200V-stack-lv3 | 5/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
803 | AV | AV Switcher | C4:42:68:65:3F:74 | switch-200V-stack-lv3 | 5/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
717 | AV | Airtame | 38:4B:76:F1:95:75 | switch-200V-stack-lv3 | 5/1/27 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1022 | AV | PDU | 28:B5:E8:6F:4A:58 | switch-200V-stack-lv3 | 5/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
805 | AV | AV Switcher | C4:42:68:65:3F:93 | switch-200V-stack-lv3 | 5/1/30 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1154 | AV | Projector | F8:25:51:CD:3F:E4 | switch-200V-stack-lv3 | 5/1/31 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
831 | AV | Display | 28:E6:A9:8D:5A:60 | switch-200V-stack-lv3 | 5/1/33 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
798 | AV | AV Switcher | C4:42:68:65:38:8A | switch-200V-stack-lv3 | 5/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1175 | AV | Projector | F8:25:51:D2:70:90 | switch-200V-stack-lv3 | 5/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1029 | AV | PDU | 28:B5:E8:6F:D1:0D | switch-200V-stack-lv3 | 5/1/44 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
731 | AV | Airtame | 8C:AE:4C:D2:00:95 | switch-200V-stack-lv3 | 5/1/46 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
794 | AV | AV Switcher | C4:42:68:65:2F:04 | switch-200V-stack-lv3 | 5/1/48 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
496 | AP | r650-3d-bf-30 | 5C:83:6C:3D:BF:30 | switch-200V-stack-lv4 | 1/1/1 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
453 | AP | r650-19-9c-c0 | C8:A6:08:19:9C:C0 | switch-200V-stack-lv4 | 1/1/2 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
452 | AP | r650-19-9c-a0 | C8:A6:08:19:9C:A0 | switch-200V-stack-lv4 | 1/1/3 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
492 | AP | r650-3d-4c-80 | 5C:83:6C:3D:4C:80 | switch-200V-stack-lv4 | 1/1/4 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
451 | AP | r650-19-9c-90 | C8:A6:08:19:9C:90 | switch-200V-stack-lv4 | 1/1/5 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
450 | AP | r650-19-9c-80 | C8:A6:08:19:9C:80 | switch-200V-stack-lv4 | 1/1/6 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
448 | AP | r650-19-9b-90 | C8:A6:08:19:9B:90 | switch-200V-stack-lv4 | 1/1/7 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
449 | AP | r650-19-9c-70 | C8:A6:08:19:9C:70 | switch-200V-stack-lv4 | 1/1/9 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
495 | AP | r650-3d-be-c0 | 5C:83:6C:3D:BE:C0 | switch-200V-stack-lv4 | 1/1/10 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
462 | AP | r650-32-66-a0 | CC:1B:5A:32:66:A0 | switch-200V-stack-lv4 | 1/1/11 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
1600 | printer | 200v-lvl4-staffroom | 34:9F:7B:5F:D4:1E | switch-200V-stack-lv4 | 1/1/12 | 1240 (200V_staff) | 2800 (VL-print-01) | Done | Master list
1028 | AV | PDU | 28:B5:E8:6F:CB:73 | switch-200V-stack-lv4 | 1/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1328 | AV | Touch Panel | C4:42:68:6D:2B:79 | switch-200V-stack-lv4 | 1/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1153 | AV | Projector | F8:25:51:CD:3F:E3 | switch-200V-stack-lv4 | 1/1/18 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
977 | AV | Occupancy Sensor | C4:42:68:65:91:53 | switch-200V-stack-lv4 | 1/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
729 | AV | Airtame | 38:4B:76:F1:A3:28 | switch-200V-stack-lv4 | 1/1/20 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1168 | AV | Projector | F8:25:51:CF:D4:66 | switch-200V-stack-lv4 | 1/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1321 | AV | Touch Panel | C4:42:68:6C:2D:D7 | switch-200V-stack-lv4 | 1/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
726 | AV | Airtame | 38:4B:76:F1:A1:72 | switch-200V-stack-lv4 | 1/1/24 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1015 | AV | PDU | 28:B5:E8:68:78:FD | switch-200V-stack-lv4 | 1/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1237 | AV | Room Camera | B8:A4:4F:CB:C5:7C | switch-200V-stack-lv4 | 1/1/26 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
808 | AV | AV Switcher | C4:42:68:65:68:A6 | switch-200V-stack-lv4 | 1/1/27 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
699 | AV | Airtame | 38:4B:76:F1:83:57 | switch-200V-stack-lv4 | 1/1/29 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1144 | AV | Projector | F8:25:51:CC:0F:80 | switch-200V-stack-lv4 | 1/1/31 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1330 | AV | Touch Panel | C4:42:68:6D:2C:10 | switch-200V-stack-lv4 | 1/1/33 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1243 | AV | Room Camera | B8:A4:4F:CB:D2:17 | switch-200V-stack-lv4 | 1/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1198 | AV | Projector Screen Right | 80:1F:12:4E:EB:71 | switch-200V-stack-lv4 | 1/1/36 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1102 | AV | Pro Convert for NDI to HDMI | D0:C8:57:80:AA:C1 | switch-200V-stack-lv4 | 1/1/37 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1332 | AV | Touch Panel | C4:42:68:6D:30:08 | switch-200V-stack-lv4 | 1/1/38 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1323 | AV | Touch Panel | C4:42:68:6C:40:90 | switch-200V-stack-lv4 | 1/1/39 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1322 | AV | Touch Panel | C4:42:68:6C:35:04 | switch-200V-stack-lv4 | 1/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1324 | AV | Touch Panel | C4:42:68:6C:42:6B | switch-200V-stack-lv4 | 1/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
894 | AV | Keypad for Room-In-Use light | C4:42:68:59:EB:95 | switch-200V-stack-lv4 | 1/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1105 | AV | Pro convert for NDI to HDMI | D0:C8:57:82:8B:22 | switch-200V-stack-lv4 | 1/1/43 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1202 | AV | PTZ Camera | DC:E2:AC:02:EC:B8 | switch-200V-stack-lv4 | 1/1/44 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1454 | cctv | cam-200v-ae-d7-00.trinity.unimelb.edu.au | 00:02:d1:ae:d7:00 | switch-200V-stack-lv4 | 2/1/1 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1456 | cctv | cam-200v-ae-d7-09.trinity.unimelb.edu.au | 00:02:d1:ae:d7:09 | switch-200V-stack-lv4 | 2/1/2 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1453 | cctv | cam-200v-AE-D6-FF.trinity.unimelb.edu.au | 00:02:d1:ae:d6:ff | switch-200V-stack-lv4 | 2/1/3 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1449 | cctv | cam-200v-AE-D6-F6.trinity.unimelb.edu.au | 00:02:d1:ae:d6:f6 | switch-200V-stack-lv4 | 2/1/4 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1448 | cctv | cam-200v-AE-D6-F5.trinity.unimelb.edu.au | 00:02:d1:ae:d6:f5 | switch-200V-stack-lv4 | 2/1/5 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1452 | cctv | cam-200v-AE-D6-F9.trinity.unimelb.edu.au | 00:02:d1:ae:d6:f9 | switch-200V-stack-lv4 | 2/1/6 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1451 | cctv | cam-200v-AE-D6-F8.trinity.unimelb.edu.au | 00:02:d1:ae:d6:f8 | switch-200V-stack-lv4 | 2/1/7 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done (pilot) | Master list
1385 | AV | Wireless Mic Receiver | 00:1B:66:39:93:93 | switch-200V-stack-lv4 | 2/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
696 | AV | Airtame | 38:4B:76:F1:4D:F1 | switch-200V-stack-lv4 | 2/1/14 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1193 | AV | Projector Screen | 80:34:28:14:46:0C | switch-200V-stack-lv4 | 2/1/15 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1326 | AV | Touch Panel | C4:42:68:6C:43:F3 | switch-200V-stack-lv4 | 2/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1047 | AV | PDU | 98:89:24:0D:AF:FA | switch-200V-stack-lv4 | 2/1/17 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
975 | AV | Occupancy Sensor | C4:42:68:65:8F:7B | switch-200V-stack-lv4 | 2/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
724 | AV | Airtame | 38:4B:76:F1:9F:90 | switch-200V-stack-lv4 | 2/1/22 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
984 | AV | Occupancy Sensor | C4:42:68:65:95:96 | switch-200V-stack-lv4 | 2/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
728 | AV | Airtame | 38:4B:76:F1:A2:70 | switch-200V-stack-lv4 | 2/1/24 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1299 | AV | Touch Panel | C4:42:68:3E:0A:00 | switch-200V-stack-lv4 | 2/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
939 | AV | Occupancy Sensor | C4:42:68:65:96:20 | switch-200V-stack-lv4 | 2/1/26 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
828 | AV | Cresnet Bridge For Outside Sign | C4:42:68:5D:50:D2 | switch-200V-stack-lv4 | 2/1/27 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
763 | AV | AV Switcher | 00:1D:56:0A:8E:47 | switch-200V-stack-lv4 | 2/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
799 | AV | AV Switcher | C4:42:68:65:38:D6 | switch-200V-stack-lv4 | 2/1/29 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
756 | AV | Audio DSP | 78:45:01:1A:93:AF | switch-200V-stack-lv4 | 2/1/30 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1235 | AV | Room Camera | B8:A4:4F:CB:C4:3D | switch-200V-stack-lv4 | 2/1/33 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
982 | AV | Occupancy Sensor | C4:42:68:65:91:9A | switch-200V-stack-lv4 | 2/1/34 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1250 | AV | Room Camera | B8:A4:4F:CE:F3:7D | switch-200V-stack-lv4 | 2/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
980 | AV | Occupancy Sensor | C4:42:68:65:91:85 | switch-200V-stack-lv4 | 2/1/36 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1217 | AV | Room Camera | B8:A4:4F:CB:CA:ED | switch-200V-stack-lv4 | 2/1/37 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
965 | AV | Occupancy Sensor | C4:42:68:65:5A:42 | switch-200V-stack-lv4 | 2/1/38 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1247 | AV | Room Camera | B8:A4:4F:CE:EB:E4 | switch-200V-stack-lv4 | 2/1/39 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
979 | AV | Occupancy Sensor | C4:42:68:65:91:77 | switch-200V-stack-lv4 | 2/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1249 | AV | Room Camera | B8:A4:4F:CE:F1:43 | switch-200V-stack-lv4 | 2/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1248 | AV | Room Camera | B8:A4:4F:CE:EF:42 | switch-200V-stack-lv4 | 2/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1246 | AV | Room Camera | B8:A4:4F:CE:EA:58 | switch-200V-stack-lv4 | 2/1/43 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
981 | AV | Occupancy Sensor | C4:42:68:65:91:8B | switch-200V-stack-lv4 | 2/1/44 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1240 | AV | Room Camera | B8:A4:4F:CB:CA:0C | switch-200V-stack-lv4 | 2/1/45 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1331 | AV | Touch Panel | C4:42:68:6D:2F:E4 | switch-200V-stack-lv4 | 2/1/46 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
804 | AV | AV Switcher | C4:42:68:65:3F:79 | switch-200V-stack-lv4 | 2/1/47 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
985 | AV | Occupancy Sensor | C4:42:68:65:95:E0 | switch-200V-stack-lv4 | 2/1/48 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
924 | AV | Mic Charger | 00:1B:66:3F:0D:8B | switch-200V-stack-lv4 | 4/1/3 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1074 | AV | PDU 1 | 28:B5:E8:6F:27:66 | switch-200V-stack-lv4 | 4/1/5 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
913 | AV | LCD Left | F8:01:B4:AE:DF:9E | switch-200V-stack-lv4 | 4/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1199 | AV | PTZ Camera | DC:E2:AC:02:EC:9D | switch-200V-stack-lv4 | 4/1/9 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1023 | AV | PDU | 28:B5:E8:6F:4F:DA | switch-200V-stack-lv4 | 4/1/11 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
897 | AV | LCD | 74:C1:7E:33:03:7A | switch-200V-stack-lv4 | 4/1/12 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1186 | AV | Projector Left | 38:1A:52:B2:00:B8 | switch-200V-stack-lv4 | 4/1/15 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1172 | AV | Projector | F8:25:51:D2:70:36 | switch-200V-stack-lv4 | 4/1/18 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1155 | AV | Projector | F8:25:51:CD:40:32 | switch-200V-stack-lv4 | 4/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1025 | AV | PDU | 28:B5:E8:6F:CB:40 | switch-200V-stack-lv4 | 4/1/24 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
795 | AV | AV Switcher | C4:42:68:65:31:AC | switch-200V-stack-lv4 | 4/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
914 | AV | LCD Right | F8:01:B4:60:4C:AB | switch-200V-stack-lv4 | 4/1/37 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1196 | AV | Projector Screen Left | 80:34:28:5C:F1:F2 | switch-200V-stack-lv4 | 4/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1212 | AV | Recorder | 00:1C:08:00:70:2D | switch-200V-stack-lv4 | 4/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1075 | AV | PDU 2 | 28:B5:E8:6F:61:FB | switch-200V-stack-lv4 | 4/1/43 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1152 | AV | Projector | F8:25:51:CD:3F:E0 | switch-200V-stack-lv4 | 5/1/4 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1018 | AV | PDU | 28:B5:E8:68:81:A6 | switch-200V-stack-lv4 | 5/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
725 | AV | Airtame | 38:4B:76:F1:A1:45 | switch-200V-stack-lv4 | 5/1/9 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
800 | AV | AV Switcher | C4:42:68:65:39:C6 | switch-200V-stack-lv4 | 5/1/10 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1026 | AV | PDU | 28:B5:E8:6F:CB:46 | switch-200V-stack-lv4 | 5/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
802 | AV | AV Switcher | C4:42:68:65:3A:3F | switch-200V-stack-lv4 | 5/1/15 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
797 | AV | AV Switcher | C4:42:68:65:37:38 | switch-200V-stack-lv4 | 5/1/20 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1017 | AV | PDU | 28:B5:E8:68:7E:6D | switch-200V-stack-lv4 | 5/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1167 | AV | Projector | F8:25:51:CF:D3:D9 | switch-200V-stack-lv4 | 5/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
901 | AV | LCD | F8:01:B4:53:86:9A | switch-200V-stack-lv4 | 5/1/30 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1020 | AV | PDU | 28:B5:E8:6F:27:3F | switch-200V-stack-lv4 | 5/1/31 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
714 | AV | Airtame | 38:4B:76:F1:92:CF | switch-200V-stack-lv4 | 5/1/32 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
727 | AV | Airtame | 38:4B:76:F1:A1:73 | switch-200V-stack-lv4 | 5/1/33 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done (pilot) | Master list
807 | AV | AV Switcher | C4:42:68:65:3F:D0 | switch-200V-stack-lv4 | 5/1/34 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
833 | AV | Display | 28:E6:A9:8D:5A:73 | switch-200V-stack-lv4 | 5/1/36 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1188 | AV | Projector Right | 38:1A:52:B2:00:9F | switch-200V-stack-lv4 | 5/1/37 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1185 | AV | Projector Left | 38:1A:52:B1:FF:B9 | switch-200V-stack-lv4 | 5/1/39 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1214 | AV | Recorder | 00:1C:08:00:71:05 | switch-200V-stack-lv4 | 5/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
926 | AV | Mic Charger | 00:1B:66:3F:15:3A | switch-200V-stack-lv4 | 5/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
716 | AV | Airtame | 38:4B:76:F1:95:43 | switch-200V-stack-lv4 | 5/1/44 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done (pilot) | Master list
1386 | AV | Wireless Mic Receiver | 00:1B:66:39:93:95 | switch-200V-stack-lv4 | 5/1/45 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
715 | AV | Airtame | 38:4B:76:F1:92:D2 | switch-200V-stack-lv4 | 5/1/46 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done (pilot) | Master list
1061 | AV | PDU | B8:80:4F:28:50:5F | switch-200V-stack-lv6 | 1/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
764 | AV | AV Switcher | 00:1D:56:0A:B4:A6 | switch-200V-stack-lv6 | 1/1/9 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
757 | AV | Audio DSP | 78:45:01:0C:7D:CC | switch-200V-stack-lv6 | 1/1/10 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
472 | AP | r650-39-4b-d0 | C8:A6:08:39:4B:D0 | switch-200V-stack-lv6 | 1/1/13 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
471 | AP | r650-39-4b-c0 | C8:A6:08:39:4B:C0 | switch-200V-stack-lv6 | 1/1/14 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
478 | AP | r650-39-52-00 | C8:A6:08:39:52:00 | switch-200V-stack-lv6 | 1/1/15 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
476 | AP | r650-39-51-00 | C8:A6:08:39:51:00 | switch-200V-stack-lv6 | 1/1/16 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
481 | AP | r650-39-54-a0 | C8:A6:08:39:54:A0 | switch-200V-stack-lv6 | 1/1/17 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
470 | AP | r650-39-4a-60 | C8:A6:08:39:4A:60 | switch-200V-stack-lv6 | 1/1/18 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
473 | AP | r650-39-4b-f0 | C8:A6:08:39:4B:F0 | switch-200V-stack-lv6 | 1/1/19 | 100 (management) | 2010 (VL-wifimgmt-01) | Done (pilot) | Master list
482 | AP | r650-39-5c-50 | C8:A6:08:39:5C:50 | switch-200V-stack-lv6 | 1/1/20 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
464 | AP | r650-39-2d-b0 | C8:A6:08:39:2D:B0 | switch-200V-stack-lv6 | 1/1/21 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
467 | AP | r650-39-35-10 | C8:A6:08:39:35:10 | switch-200V-stack-lv6 | 1/1/22 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
479 | AP | r650-39-52-90 | C8:A6:08:39:52:90 | switch-200V-stack-lv6 | 1/1/23 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
465 | AP | r650-39-33-f0 | C8:A6:08:39:33:F0 | switch-200V-stack-lv6 | 1/1/24 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
466 | AP | r650-39-34-60 | C8:A6:08:39:34:60 | switch-200V-stack-lv6 | 1/1/25 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
468 | AP | r650-39-36-80 | C8:A6:08:39:36:80 | switch-200V-stack-lv6 | 1/1/26 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
474 | AP | r650-39-4c-f0 | C8:A6:08:39:4C:F0 | switch-200V-stack-lv6 | 1/1/27 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
477 | AP | r650-39-51-e0 | C8:A6:08:39:51:E0 | switch-200V-stack-lv6 | 1/1/28 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
480 | AP | r650-39-54-60 | C8:A6:08:39:54:60 | switch-200V-stack-lv6 | 1/1/29 | 100 (management) | 2010 (VL-wifimgmt-01) | Done | Master list
1443 | cctv | cam-200V2B23.trinity.unimelb.edu.au | c0:56:e3:85:a5:61 | switch-200V-stack-lv6 | 1/1/37 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done | Master list
1444 | cctv | cam-200V2F10.trinity.unimelb.edu.au | c0:56:e3:85:a4:d8 | switch-200V-stack-lv6 | 1/1/38 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done | Master list
1442 | cctv | cam-200V1D05.trinity.unimelb.edu.au | c0:56:e3:85:a5:2a | switch-200V-stack-lv6 | 1/1/39 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done | Master list
1445 | cctv | cam-200V2K14.trinity.unimelb.edu.au | c0:56:e3:85:a5:6d | switch-200V-stack-lv6 | 1/1/40 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) | Done | Master list
927 | AV | NDI-HDMI Decoder | D0:C8:57:81:64:1F | switch-200V-stack-lv6 | 2/1/1 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1224 | AV | Room Camera | B8:A4:4F:68:F5:19 | switch-200V-stack-lv6 | 2/1/2 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1138 | AV | Projector | F8:25:51:CB:8C:9B | switch-200V-stack-lv6 | 2/1/3 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1306 | AV | Touch Panel | C4:42:68:2C:3C:0A | switch-200V-stack-lv6 | 2/1/14 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
702 | AV | Airtame | 38:4B:76:F1:89:2C | switch-200V-stack-lv6 | 2/1/15 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
762 | AV | AV Switcher | 00:1D:56:09:CE:57 | switch-200V-stack-lv6 | 2/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1054 | AV | PDU | B8:80:4F:18:2D:88 | switch-200V-stack-lv6 | 2/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1310 | AV | Touch Panel | C4:42:68:2C:3D:36 | switch-200V-stack-lv6 | 2/1/17 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1280 | AV | Room NUC | 48:21:0B:56:AE:39 | switch-200V-stack-lv6 | 2/1/18 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
766 | AV | AV Switcher | 00:1D:56:0A:DF:BB | switch-200V-stack-lv6 | 2/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1051 | AV | PDU | B8:80:4F:18:1C:F0 | switch-200V-stack-lv6 | 2/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
703 | AV | Airtame | 38:4b:76:f1:89:48 | switch-200V-stack-lv6 | 2/1/20 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1267 | AV | Room NUC | 48:21:0B:56:AC:B1 | switch-200V-stack-lv6 | 2/1/21 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
1308 | AV | Touch Panel | C4:42:68:2C:3C:C0 | switch-200V-stack-lv6 | 2/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
770 | AV | AV Switcher | 00:1D:56:0A:DF:C3 | switch-200V-stack-lv6 | 2/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1059 | AV | PDU | B8:80:4F:28:4C:8A | switch-200V-stack-lv6 | 2/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
709 | AV | Airtame | 38:4b:76:f1:8f:ef | switch-200V-stack-lv6 | 2/1/24 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1262 | AV | Room NUC | 48:21:0B:56:AA:D3 | switch-200V-stack-lv6 | 2/1/25 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
1303 | AV | Touch Panel | C4:42:68:1A:48:25 | switch-200V-stack-lv6 | 2/1/26 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
713 | AV | Airtame | 38:4b:76:f1:90:1e | switch-200V-stack-lv6 | 2/1/27 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
767 | AV | AV Switcher | 00:1D:56:0A:DF:BC | switch-200V-stack-lv6 | 2/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1055 | AV | PDU | B8:80:4F:18:31:9C | switch-200V-stack-lv6 | 2/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1265 | AV | Room NUC | 48:21:0B:56:AB:F9 | switch-200V-stack-lv6 | 2/1/29 | 1240 (200V_staff) | 2700 (VL-av-01) | Done (pilot) | Master list
765 | AV | AV Switcher | 00:1D:56:0A:DF:BA | switch-200V-stack-lv6 | 2/1/30 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1057 | AV | PDU | B8:80:4F:28:19:F6 | switch-200V-stack-lv6 | 2/1/30 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1261 | AV | Room NUC | 48:21:0B:56:AA:BC | switch-200V-stack-lv6 | 2/1/31 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
941 | AV | Occupancy Sensor | B8:98:B0:0F:1C:5D | switch-200V-stack-lv6 | 2/1/32 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1218 | AV | Room Camera | B8:A4:4F:49:4A:9B | switch-200V-stack-lv6 | 2/1/33 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1302 | AV | Touch Panel | C4:42:68:15:2D:E5 | switch-200V-stack-lv6 | 2/1/34 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
1200 | AV | PTZ Camera | DC:E2:AC:02:E4:DA | switch-200V-stack-lv6 | 2/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
943 | AV | Occupancy Sensor | B8:98:B0:0F:1C:5F | switch-200V-stack-lv6 | 2/1/36 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1225 | AV | Room Camera | B8:A4:4F:68:FE:85 | switch-200V-stack-lv6 | 2/1/37 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1317 | AV | Touch Panel | C4:42:68:38:BB:41 | switch-200V-stack-lv6 | 2/1/38 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
956 | AV | Occupancy Sensor | B8:98:B0:0F:1C:78 | switch-200V-stack-lv6 | 2/1/39 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1227 | AV | Room Camera | B8:A4:4F:69:AB:10 | switch-200V-stack-lv6 | 2/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1130 | AV | Projector | F8:25:51:CB:8C:6E | switch-200V-stack-lv6 | 2/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1110 | AV | Projector | 38:1A:52:B1:75:B7 | switch-200V-stack-lv6 | 2/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1314 | AV | Touch Panel | C4:42:68:33:59:A9 | switch-200V-stack-lv6 | 2/1/43 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
944 | AV | Occupancy Sensor | B8:98:B0:0F:1C:63 | switch-200V-stack-lv6 | 2/1/44 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1221 | AV | Room Camera | B8:A4:4F:49:85:78 | switch-200V-stack-lv6 | 2/1/45 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1278 | AV | Room NUC | 48:21:0B:56:AE:12 | switch-200V-stack-lv6 | 3/1/11 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
721 | AV | Airtame | 38:4b:76:f1:9a:d0 | switch-200V-stack-lv6 | 3/1/12 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
775 | AV | AV Switcher | 00:1D:56:0A:E0:4F | switch-200V-stack-lv6 | 3/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1066 | AV | PDU | B8:80:4F:28:58:6F | switch-200V-stack-lv6 | 3/1/13 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1305 | AV | Touch Panel | C4:42:68:2A:71:B4 | switch-200V-stack-lv6 | 3/1/14 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1260 | AV | Room NUC | 48:21:0B:56:AA:62 | switch-200V-stack-lv6 | 3/1/15 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
700 | AV | Airtame | 38:4b:76:f1:89:26 | switch-200V-stack-lv6 | 3/1/16 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1312 | AV | Touch Panel | C4:42:68:2C:3D:B9 | switch-200V-stack-lv6 | 3/1/17 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
774 | AV | AV Switcher | 00:1D:56:0A:E0:4E | switch-200V-stack-lv6 | 3/1/18 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1053 | AV | PDU | B8:80:4F:18:26:32 | switch-200V-stack-lv6 | 3/1/18 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
711 | AV | Airtame | 38:4b:76:f1:90:1c | switch-200V-stack-lv6 | 3/1/19 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1258 | AV | Room NUC | 48:21:0B:56:98:6C | switch-200V-stack-lv6 | 3/1/20 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1316 | AV | Touch Panel | C4:42:68:38:BB:1E | switch-200V-stack-lv6 | 3/1/24 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1340 | AV | Touch Panel | C4:42:68:1C:E2:1B | switch-200V-stack-lv6 | 3/1/25 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1129 | AV | Projector | F8:25:51:CB:8C:6B | switch-200V-stack-lv6 | 3/1/26 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1254 | AV | Room Camera | B8:A4:4F:69:B2:70 | switch-200V-stack-lv6 | 3/1/27 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
998 | AV | Occupancy Sensor | B8:98:B0:0F:1C:73 | switch-200V-stack-lv6 | 3/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1311 | AV | Touch Panel | C4:42:68:2C:3D:5F | switch-200V-stack-lv6 | 3/1/29 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1234 | AV | Room Camera | B8:A4:4F:69:D0:DE | switch-200V-stack-lv6 | 3/1/30 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
942 | AV | Occupancy Sensor | B8:98:B0:0F:1C:5E | switch-200V-stack-lv6 | 3/1/31 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1304 | AV | Touch Panel | C4:42:68:2A:6C:B0 | switch-200V-stack-lv6 | 3/1/32 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1226 | AV | Room Camera | B8:A4:4F:68:FE:98 | switch-200V-stack-lv6 | 3/1/33 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
947 | AV | Occupancy Sensor | B8:98:B0:0F:1C:68 | switch-200V-stack-lv6 | 3/1/34 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1309 | AV | Touch Panel | C4:42:68:2C:3C:FE | switch-200V-stack-lv6 | 3/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1228 | AV | Room Camera | B8:A4:4F:69:AE:62 | switch-200V-stack-lv6 | 3/1/36 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
949 | AV | Occupancy Sensor | B8:98:B0:0F:1C:6B | switch-200V-stack-lv6 | 3/1/37 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
953 | AV | Occupancy Sensor | B8:98:B0:0F:1C:6F | switch-200V-stack-lv6 | 3/1/38 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1220 | AV | Room Camera | B8:A4:4F:49:82:9A | switch-200V-stack-lv6 | 3/1/39 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
955 | AV | Occupancy Sensor | B8:98:B0:0F:1C:75 | switch-200V-stack-lv6 | 3/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1219 | AV | Room Camera | B8:A4:4F:49:55:98 | switch-200V-stack-lv6 | 3/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
954 | AV | Occupancy Sensor | B8:98:B0:0F:1C:70 | switch-200V-stack-lv6 | 3/1/42 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1230 | AV | Room Camera | B8:A4:4F:69:AE:77 | switch-200V-stack-lv6 | 3/1/43 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
945 | AV | Occupancy Sensor | B8:98:B0:0F:1C:65 | switch-200V-stack-lv6 | 3/1/44 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1231 | AV | Room Camera | B8:A4:4F:69:B2:86 | switch-200V-stack-lv6 | 3/1/45 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
950 | AV | Occupancy Sensor | B8:98:B0:0F:1C:6C | switch-200V-stack-lv6 | 3/1/46 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1233 | AV | Room Camera | B8:A4:4F:69:D0:9F | switch-200V-stack-lv6 | 3/1/47 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
951 | AV | Occupancy Sensor | B8:98:B0:0F:1C:6D | switch-200V-stack-lv6 | 3/1/48 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1315 | AV | Touch Panel | C4:42:68:38:BA:E0 | switch-200V-stack-lv6 | 4/1/4 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1190 | AV | Projector Screen | 04:91:62:D7:90:01 | switch-200V-stack-lv6 | 4/1/5 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1232 | AV | Room Camera | B8:A4:4F:69:D0:8F | switch-200V-stack-lv6 | 4/1/6 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1313 | AV | Touch Panel | C4:42:68:2C:B4:62 | switch-200V-stack-lv6 | 4/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
952 | AV | Occupancy Sensor | B8:98:B0:0F:1C:6E | switch-200V-stack-lv6 | 4/1/10 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1222 | AV | Room Camera | B8:A4:4F:68:F4:DA | switch-200V-stack-lv6 | 4/1/11 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
946 | AV | Occupancy Sensor | B8:98:B0:0F:1C:67 | switch-200V-stack-lv6 | 4/1/12 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
720 | AV | Airtame | 38:4b:76:f1:9a:cd | switch-200V-stack-lv6 | 4/1/13 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
776 | AV | AV Switcher | 00:1D:56:0A:E0:53 | switch-200V-stack-lv6 | 4/1/14 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1058 | AV | PDU | B8:80:4F:28:1D:83 | switch-200V-stack-lv6 | 4/1/15 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1162 | AV | Projector | F8:25:51:CF:6E:65 | switch-200V-stack-lv6 | 4/1/16 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1319 | AV | Touch Panel | C4:42:68:38:BB:AC | switch-200V-stack-lv6 | 4/1/17 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1274 | AV | Room NUC | 48:21:0B:56:AD:69 | switch-200V-stack-lv6 | 4/1/18 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
948 | AV | Occupancy Sensor | B8:98:B0:0F:1C:6A | switch-200V-stack-lv6 | 4/1/19 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1229 | AV | Room Camera | B8:A4:4F:69:AE:6F | switch-200V-stack-lv6 | 4/1/20 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
707 | AV | Airtame | 38:4b:76:f1:8f:eb | switch-200V-stack-lv6 | 4/1/21 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
778 | AV | AV Switcher | 00:1D:56:0A:E0:88 | switch-200V-stack-lv6 | 4/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1063 | AV | PDU | B8:80:4F:28:54:6D | switch-200V-stack-lv6 | 4/1/22 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1282 | AV | Room NUC | 48:21:0B:56:AE:56 | switch-200V-stack-lv6 | 4/1/23 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
1686 | PhysicalAccess | cloe-000-200v | 00:11:B9:08:2B:67 | switch-200V-stack-lv6 | 4/1/24 | 1213 (200V_building) | 2510 (VL-bac-01) | Done | Matched from 200V tab
1602 | printer | 200v-lvl-5-quiet-study | 40:F8:DF:64:BE:D6 | switch-200V-stack-lv6 | 5/1/1 | 1240 (200V_staff) | 2800 (VL-print-01) | Done | Master list
1191 | AV | Projector Screen | 04:91:62:D7:95:5D | switch-200V-stack-lv6 | 5/1/34 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1601 | printer | 200v-lvl-5-eap-office | 6C:3C:7C:BE:91:93 | switch-200V-stack-lv6 | 5/1/38 | 1240 (200V_staff) | 2800 (VL-print-01) | Done | Master list
1603 | printer | 200v-lvl-5-staffroom2 | 6C:3C:7C:BE:C0:A9 | switch-200V-stack-lv6 | 5/1/42 | 1240 (200V_staff) | 2800 (VL-print-01) | Done | Master list
1211 | AV | Recorder | 00:1C:08:00:6B:B7 | switch-200V-stack-lv6 | 6/1/20 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
722 | AV | Airtame | 38:4b:76:f1:9a:d1 | switch-200V-stack-lv6 | 6/1/24 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
704 | AV | Airtame | 38:4b:76:f1:89:59 | switch-200V-stack-lv6 | 6/1/26 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
768 | AV | AV Switcher | 00:1D:56:0A:DF:BD | switch-200V-stack-lv6 | 6/1/27 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1056 | AV | PDU | B8:80:4F:18:74:D1 | switch-200V-stack-lv6 | 6/1/27 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1272 | AV | Room NUC | 48:21:0B:56:AD:2C | switch-200V-stack-lv6 | 6/1/28 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
1163 | AV | Projector | F8:25:51:CF:6E:6D | switch-200V-stack-lv6 | 6/1/34 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
712 | AV | Airtame | 38:4b:76:f1:90:1d | switch-200V-stack-lv6 | 6/1/35 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done (pilot) | Master list
1269 | AV | Room NUC | 48:21:0B:56:AC:F2 | switch-200V-stack-lv6 | 6/1/38 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
706 | AV | Airtame | 38:4b:76:f1:89:60 | switch-200V-stack-lv6 | 6/1/39 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
777 | AV | AV Switcher | 00:1D:56:0A:E0:87 | switch-200V-stack-lv6 | 6/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1052 | AV | PDU | B8:80:4F:18:22:12 | switch-200V-stack-lv6 | 6/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1137 | AV | Projector | F8:25:51:CB:8C:9A | switch-200V-stack-lv6 | 6/1/41 | 1230 (200V_av) | 2700 (VL-av-01) | Done (pilot) | Master list
899 | AV | LCD | A8:4A:63:30:73:65 | switch-200V-stack-lv6 | 6/1/45 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
900 | AV | LCD | A8:4A:63:30:73:E3 | switch-200V-stack-lv6 | 6/1/46 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1135 | AV | Projector | F8:25:51:CB:8C:95 | switch-200V-stack-lv6 | 7/1/3 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1140 | AV | Projector | F8:25:51:CB:8C:A9 | switch-200V-stack-lv6 | 7/1/4 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1124 | AV | Projector | F8:25:51:CB:8A:CE | switch-200V-stack-lv6 | 7/1/5 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1127 | AV | Projector | F8:25:51:CB:8B:46 | switch-200V-stack-lv6 | 7/1/8 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1136 | AV | Projector | F8:25:51:CB:8C:97 | switch-200V-stack-lv6 | 7/1/9 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
701 | AV | Airtame | 38:4b:76:f1:89:2b | switch-200V-stack-lv6 | 7/1/10 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
1126 | AV | Projector | F8:25:51:CB:8B:41 | switch-200V-stack-lv6 | 7/1/11 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1060 | AV | PDU | B8:80:4F:28:50:35 | switch-200V-stack-lv6 | 7/1/14 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1128 | AV | Projector | F8:25:51:CB:8C:69 | switch-200V-stack-lv6 | 7/1/17 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1604 | printer | 200v-lvl-6-staff-corridor | 34:9F:7B:5E:35:55 | switch-200V-stack-lv6 | 7/1/19 | 1240 (200V_staff) | 2800 (VL-print-01) | Done | Master list
735 | AV | Airtame | 38:4b:76:f1:89:5e | switch-200V-stack-lv6 | 7/1/22 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
783 | AV | AV Switcher | 00:1D:56:0A:E0:89 | switch-200V-stack-lv6 | 7/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1069 | AV | PDU | B8:80:4F:28:19:F0 | switch-200V-stack-lv6 | 7/1/23 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1288 | AV | Room NUC | 48:21:0B:56:AE:2F | switch-200V-stack-lv6 | 7/1/24 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
723 | AV | Airtame | 38:4b:76:f1:9a:d4 | switch-200V-stack-lv6 | 7/1/27 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
773 | AV | AV Switcher | 00:1D:56:0A:E0:4D | switch-200V-stack-lv6 | 7/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1062 | AV | PDU | B8:80:4F:28:54:5B | switch-200V-stack-lv6 | 7/1/28 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1259 | AV | Room NUC | 48:21:0B:56:AA:57 | switch-200V-stack-lv6 | 7/1/30 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
710 | AV | Airtame | 38:4b:76:f1:90:19 | switch-200V-stack-lv6 | 7/1/31 | 1272 (200V_w_wifi) | 2700 (VL-av-01) | Done | Master list
771 | AV | AV Switcher | 00:1D:56:0A:E0:35 | switch-200V-stack-lv6 | 7/1/32 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1065 | AV | PDU | B8:80:4F:28:58:54 | switch-200V-stack-lv6 | 7/1/32 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1273 | AV | Room NUC | 48:21:0B:56:AD:53 | switch-200V-stack-lv6 | 7/1/33 | 1240 (200V_staff) | 2700 (VL-av-01) | Done | Master list
1139 | AV | Projector | F8:25:51:CB:8C:A8 | switch-200V-stack-lv6 | 7/1/34 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
772 | AV | AV Switcher | 00:1D:56:0A:E0:36 | switch-200V-stack-lv6 | 7/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1067 | AV | PDU | B8:80:4F:28:5C:11 | switch-200V-stack-lv6 | 7/1/35 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1125 | AV | Projector | F8:25:51:CB:8B:3D | switch-200V-stack-lv6 | 7/1/40 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list
1111 | AV | Projector | 38:1A:52:B1:75:B8 | switch-200V-stack-lv6 | 7/1/44 | 1230 (200V_av) | 2700 (VL-av-01) | Done | Master list

## Switches
Hostname | Role | Hardware | Config file (by MAC) | Uplink to core | 200V devices | To do | Management IP | 9 Oct 2026 result | 26 Oct 2026 result
trinity200V-core | Core / gateway for new VLANs | 2 x ICX8200-24FX stack | B0_7C_51_1F_8C_06 | n/a | n/a | n/a | 10.20.8.2 (ve 1960) | Reloaded for system-max 40. WIFIMGMT-IN ACL: added seq 23/24 (SmartZone private IPs) and seq 25 (RADIUS 10.128.131.7) - unplanned, see Review 91 and 107. Saved | Not changed (ve 2000 10.21.0.1 is the gateway for the switch management addresses)
switch-200V-stack-lv3 | Access | 5 x ICX8200 stack | 80_F0_CF_38_0D_C2 | lag 3 (lvl3) | 93 | 0 | 10.21.0.27 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.22 (ve 100) | Cutover done, 84 ports. system-max 40 active. Review tab change: 7 ports (5 to 2100, 2 to 2530). Saved. 1/1/48 left on 100. Unlisted AV: 8 ports 1230 -> 2700. 10 Oct: 7 outlets (20:7B:D2:30 devices) 1230 -> 2100. 10 Oct: 3/1/20 (staff PC) 1240 -> 2100 | Port clean-up: 32 ports (Trinity column Q, 16 Oct export). Management moved to 10.21.0.27, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved. First Part B attempt rolled back by the reload timer (7:06 pm); second attempt OK.
switch-200V-stack-lv4 | Access | 5 x ICX8200 stack | 80_F0_CF_37_FD_84 | lag 2 (lvl4) | 110 | 0 | 10.21.0.26 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.21 (ve 100) | Cutover done, 89 ports. system-max 40 active. Confirm APs online. Review tab change: 3/1/7, 3/1/28 to 2100 (no link). 1/1/48 left on 100. Confirm write memory. Unlisted AV: 8 ports 1230 -> 2700. 10 Oct: 6 outlets (20:7B:D2:30 devices) 1230 -> 2100. 10 Oct: 4/1/30 1230 -> 2700, 4/1/19 (Airtame) 1272 -> 2700, 3/1/1 (staff PC) 1240 -> 2100 | Port clean-up: 54 ports (Trinity column Q, 16 Oct export). Management moved to 10.21.0.26, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved. SmartZone HTTP 500 until old IP removed and agent restarted.
switch-200V-stack-lv6 | Access | 7 x ICX8200 stack | 3C_46_A1_07_54_4E | lag 1 (lvl6) | 167 | 0 | 10.21.0.20 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.11 (ve 100) | Cutover done, 145 ports. system-max 40 active, STP on 2600/2700. Units 3/4 left the stack 20:03 and 22:44 on 9 Oct; out until unit 3 power cycled 13:35 on 10 Oct (unit 3 hangs; TAC/RMA). Saved. Review tab change: 8 ports to 2100. Saved | Port clean-up: 144 ports (Trinity column Q, 16 Oct export). Management moved to 10.21.0.20, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved. 1/1/32 had no MAC when checked.
switch-200V-LT2-1 | Access | 1 x ICX8200-24P | 3C_46_A1_05_28_AC | lag 5 (LT01), LT2-1 ports 1/2/1-1/2/2 to core 1/1/5 + 2/1/5 (LLDP) | 16 | 0 | 10.21.0.21 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.12 (ve 100) | Cutover done, 16 ports. system-max 40 active | Port clean-up: 5 ports (Trinity column Q, 16 Oct export). Management moved to 10.21.0.21, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved.
switch-200V-LT2-2 | Access | 1 x ICX7150-C12 | 10_F0_68_0C_06_D6 | Via LT2-1 port 1/1/23 (their 1/1/12), confirmed by LLDP | 0 | 0 | 10.21.0.22 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.13 (ve 100) | system-max 40 only; no port changes | Port clean-up: 11 ports (Trinity column Q, 16 Oct export). Management moved to 10.21.0.22, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved. 1/1/1 tagged-only with 2000-2953.
switch-200V-LT2-3 | Access | 1 x ICX7150-C12 | 10_F0_68_0B_D2_3E | Via LT2-1 port 1/1/24 (their 1/1/12), confirmed by LLDP | 0 | 0 | 10.21.0.23 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.14 (ve 100) | system-max 40. Review tab change: 1/1/4 to 2100 (no link). Saved | Port clean-up: 10 ports (Trinity column Q, 16 Oct export). Management moved to 10.21.0.23, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved.
switch-200V-8 | Access | 1 x ICX7150-C12 | 10_F0_68_0B_D2_2C | lag 4 (v08) | 0 | 0 | 10.21.0.25 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.16 (ve 100) | system-max 40 only; no port changes | Port clean-up: 10 ports (Trinity column Q, 16 Oct export). Management moved to 10.21.0.25, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved. UPS cards 1/1/7-1/1/9 to 2000 (DHCP); DNS servers added.
switch-200V-Tutorial-6.03 | Access | 1 x ICX7150-C12 | 10_F0_68_0B_D2_62 | lag 6 (SW6.03) | 6 | 0 | 10.21.0.24 (ve 2000, VLAN 2000), from 26 Oct; was 192.168.122.15 (ve 100) | Cutover done, 6 ports + 1/1/3 and 1/1/9 (added on site). system-max 40 active. Confirm write memory | Port clean-up: 1 port (Trinity column Q, 16 Oct export). Management moved to 10.21.0.24, default route via 10.21.0.1, management source ve 2000, old IP removed. Saved.
Total |  |  |  |  | 392 | 0
Note: on 26 Oct 2026 the access switches' management moved from VLAN 100 (ve 100, 192.168.122.0/22) to VLAN 2000 (ve 2000, 10.21.0.20 - .27, gateway 10.21.0.1). The core stays on ve 1960 (10.20.8.2).

## Port clean-up 26 Oct
Port clean-up from Trinity's switch port export (16 Oct 2026, column Q), applied 26 Oct 2026 on all 8 switches
Switch | Port | Old untagged VLAN | Tagged VLANs removed | New untagged VLAN | Link 16 Oct | MAC 16 Oct | Note | Status
switch-200V-stack-lv6 | 1/1/1 | 1240 | 1230, 1250, 1271, 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/2 | 1240 | 1230, 1250, 1271, 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/4 | 1240 | 1230, 1250, 1271, 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/5 | 1240 | 1230, 1250, 1271, 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/7 | 1240 | 1230, 1250, 1271, 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/11 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/12 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/30 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/32 | 1240 | 1272, 1273 | 2100 | Up | 1C:1A:DF:C2:4F:5E |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/33 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/34 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/35 | 100 | 1212, 1213, 1230, 1240, 1250, 1271, 1272, 1273 | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/36 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/41 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/42 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/43 | 1240 | 1272, 1273 | 2100 | Up | A0:4A:5E:E7:E8:70 |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/44 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/45 | 1240 | 1272 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/46 | 1240 | 1272, 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/47 | 1240 | 1273 | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 1/1/48 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/4 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/5 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/6 | 1240 |  | 2100 | Up | 1C:1A:DF:C2:51:28 |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/7 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/8 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/9 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/10 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/11 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/12 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/13 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 2/1/48 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/2 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/3 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/4 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/5 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/6 | 1240 |  | 2100 | Up | 1C:1A:DF:C2:51:01 |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/7 | 1240 |  | 2100 | Up | 1C:1A:DF:C0:98:69 |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/8 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/9 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/10 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/21 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/22 | 1240 |  | 2100 | Up | 1C:1A:DF:C0:9A:AB |  | Done 26 Oct
switch-200V-stack-lv6 | 3/1/23 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 4/1/2 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 4/1/3 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 4/1/7 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 4/1/9 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/2 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/3 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/4 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/5 | 1240 |  | 2100 | Up | 1C:1A:DF:C2:51:DF |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/6 | 1240 |  | 2100 | Up |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/7 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/8 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/9 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/10 | 1240 |  | 2100 | Up | 1C:1A:DF:C0:9A:52 |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/11 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/12 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/13 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/14 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/15 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/16 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/17 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/18 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/19 | 1240 |  | 2100 | Up | 1C:1A:DF:C2:50:05 |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/20 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/21 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/22 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/23 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/24 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/25 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/26 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/27 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/28 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/29 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/31 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/32 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/33 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/35 | 100 | 230, 1212, 1213, 1230, 1250, 1271, 1272, 1273 | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/36 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/37 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/39 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/40 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/41 | 1240 |  | 2100 | Up | 4C:C5:D9:D0:8D:23 |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/43 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/44 | 1240 |  | 2100 | Up | 1C:1A:DF:C2:45:3F |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/45 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/46 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 5/1/47 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/1 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/2 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/3 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/4 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/5 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/6 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/7 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/8 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/9 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/10 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/11 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/12 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/13 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/14 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/15 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/17 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/18 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/19 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/21 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/23 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/25 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/29 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/32 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/33 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/36 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/37 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/42 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/43 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/44 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/47 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 6/1/48 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/2 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/6 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/7 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/12 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/13 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/15 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/16 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/18 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/20 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/21 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/25 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/26 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/29 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/36 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/37 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/38 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/39 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/41 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/42 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/45 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/46 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/47 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv6 | 7/1/48 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-1 | 1/1/2 | 100 | 1212, 1213, 1230, 1240, 1250, 1271, 1272, 1273 | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-LT2-1 | 1/1/3 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-LT2-1 | 1/1/19 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-LT2-1 | 1/1/21 | 1240 |  | 2100 | Up | 48:21:0B:56:AC:A4 |  | Done 26 Oct
switch-200V-LT2-1 | 1/1/22 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/1 | 1240 | 1212, 1213, 1230, 1250, 1271, 1272, 1273 | none (tagged-only 2000-2953) | Down |  | item 3, decision 22 Oct: remove old VLANs only. Port becomes tagged-only with 2000 - 2953 (no untagged VLAN) | Done 26 Oct
switch-200V-LT2-2 | 1/1/2 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/3 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/4 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/5 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/6 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/7 | 1240 |  | 2100 | Up |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/8 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/9 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/10 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-2 | 1/1/11 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/1 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/2 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/3 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/5 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/6 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/7 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/8 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/9 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/10 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-LT2-3 | 1/1/11 | 1240 | 100 | 2100 | Down |  |  | Done 26 Oct
switch-200V-Tutorial-6.03 | 1/1/11 | 100 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-8 | 1/1/1 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-8 | 1/1/2 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-8 | 1/1/3 | 1240 |  | 2100 | Up | 1C:1A:DF:C0:99:7F |  | Done 26 Oct
switch-200V-8 | 1/1/4 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-8 | 1/1/5 | 1240 |  | 2100 | Up | AC:B4:80:F1:61:27 |  | Done 26 Oct
switch-200V-8 | 1/1/7 | 1240 |  | 2000 | Up | 00:09:F5:32:DB:15 | item 2, Trinity 22 Oct: UPS card 00:09:F5:32:DB:15 to 2000 | Done 26 Oct
switch-200V-8 | 1/1/8 | 1240 |  | 2000 | Up | 00:09:F5:32:DB:D1 | item 2, Trinity 22 Oct: UPS card 00:09:F5:32:DB:D1 to 2000 | Done 26 Oct
switch-200V-8 | 1/1/9 | 1240 |  | 2000 | Up | 00:09:F5:32:DB:14 | item 2, Trinity 22 Oct: UPS card 00:09:F5:32:DB:14 to 2000 | Done 26 Oct
switch-200V-8 | 1/1/10 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-8 | 1/1/11 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 1/1/8 | 100 | 1272, 1273, 2300, 2310, 2311, 2320, 2321, 2900 | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 1/1/17 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 1/1/32 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 2/1/8 | 1212 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 2/1/18 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 2/1/20 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/4 | 1240 |  | 2100 | Up | A0:4A:5E:E7:35:43 |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/5 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/9 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/11 | 1240 |  | 2100 | Up |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/13 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/14 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/19 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/20 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/21 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/22 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/27 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/29 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/30 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/35 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/37 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/39 | 1240 |  | 2100 | Up | 1C:1A:DF:C2:51:D3 |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/42 | 1240 |  | 2100 | Up | 4C:C5:D9:CD:B4:CC |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/43 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/45 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/47 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 3/1/48 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/1 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/2 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/7 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/10 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/16 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/17 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/27 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/28 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/29 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/31 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/32 | 1272 |  | 2100 | Down |  | item 1, Trinity 22 Oct: 20:7B:D2:30:99:15 (200V4H9) to 2100 | Done 26 Oct
switch-200V-stack-lv4 | 4/1/38 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/39 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 4/1/44 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/1 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/2 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/5 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/14 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/16 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/19 | 1272 |  | 2100 | Down |  | item 1, Trinity 22 Oct: 20:7B:D2:30:99:25 (200V4I17) to 2100 | Done 26 Oct
switch-200V-stack-lv4 | 5/1/24 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/26 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/35 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/38 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/40 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/43 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv4 | 5/1/47 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 1/1/12 | 100 | 1212, 1213, 1230, 1240, 1250, 1271, 1272, 1273 | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 1/1/34 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 2/1/14 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 2/1/24 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 2/1/27 | 1230 |  | 2100 | Down |  | item 1, Trinity 22 Oct: 20:7B:D2:30:98:C1 (200V3J14) to 2100 | Done 26 Oct
switch-200V-stack-lv3 | 2/1/34 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/3 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/7 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/10 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/11 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/13 | 1240 |  | 2100 | Up | 1C:1A:DF:C2:51:C2 |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/15 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/16 | 1240 |  | 2100 | Up | A0:4A:5E:E7:D5:7C |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/19 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/27 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 3/1/28 | 230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 4/1/2 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 4/1/23 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 4/1/24 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 4/1/25 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 4/1/26 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 4/1/27 | 1240 |  | 2100 | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 4/1/45 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/4 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/5 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/6 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/7 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/13 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/15 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/20 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/32 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct
switch-200V-stack-lv3 | 5/1/43 | 1230 |  | 1 (default) | Down |  |  | Done 26 Oct

## Ports without device
Switch name | Port | Untagged VLAN | New VLAN | Tagged VLANs | MACs seen (200V tab) | MAC(s) seen | Note
switch-200V-8 | 1/1/1 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/3 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/6 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-8 | 1/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/8 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/10 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-8 | 1/1/12 | None (tagged only) | n/a (trunk) | 100,1212,1213,1230,1240,1250,1271,1272,1273,2000,2010,2020,2100,2200,2300,2310,2320,2400,2500,2510,2520,2530,2600,2700,2800,2810,2900 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-LT2-1 | 1/1/2 | 100 (management) | 2010 (VL-wifimgmt-01) | 1212,1213,1230,1240,1250,1271,1272,1273 | 0
switch-200V-LT2-1 | 1/1/3 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-LT2-1 | 1/1/9 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | 00:50:56:05:43:F1
switch-200V-LT2-1 | 1/1/19 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-LT2-1 | 1/1/21 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 48:21:0B:56:AC:A4 | LLDP: CLA-TAN3130059J (NUC, MAC 48:21:0B:56:AC:A4), not in device list
switch-200V-LT2-1 | 1/1/22 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-LT2-1 | 1/1/23 | None (tagged only) | n/a (trunk) | 100,1212,1213,1230,1240,1250,1271,1272,1273,2000,2010,2020,2100,2200,2300,2310,2320,2400,2500,2510,2520,2530,2600,2700,2800,2810,2900,2950,2951,2952,2953 | 2 | 10:F0:68:0C:06:E1, 10:F0:68:0C:06:D6 | Uplink to switch-200V-LT2-2 (LLDP)
switch-200V-LT2-1 | 1/1/24 | None (tagged only) | n/a (trunk) | 100,1212,1213,1230,1240,1250,1271,1272,1273,2000,2010,2020,2100,2200,2300,2310,2320,2400,2500,2510,2520,2530,2600,2700,2800,2810,2900,2950,2951,2952,2953 | 3 | 10:F0:68:0B:D2:49, 10:F0:68:0B:D2:3E, AC:B4:80:F1:61:7F | Uplink to switch-200V-LT2-3 (LLDP)
switch-200V-LT2-2 | 1/1/1 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1212,1213,1230,1250,1271,1272,1273,2000,2010,2020,2100,2200,2300,2310,2320,2400,2500,2510,2520,2530,2600,2700,2800,2810,2900,2950,2951,2952,2953 | 0
switch-200V-LT2-2 | 1/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/3 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/6 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/8 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/10 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-LT2-2 | 1/1/12 | None (tagged only) | n/a (trunk) | 100,1212,1213,1230,1240,1250,1271,1272,1273,2000,2010,2020,2100,2200,2300,2310,2320,2400,2500,2510,2520,2530,2600,2700,2800,2810,2900,2950,2951,2952,2953 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-LT2-3 | 1/1/1 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/2 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/3 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/4 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 1 | d4:a2:cd:e1:dd:0e | Moved 9 Oct (Review tab change).
switch-200V-LT2-3 | 1/1/5 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/6 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/7 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/8 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/9 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/10 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/11 | 1240 (200v_staff) | 2100 (VL-staff-wired-01) | 100 | 0
switch-200V-LT2-3 | 1/1/12 | None (tagged only) | n/a (trunk) | 100,1212,1213,1230,1240,1250,1271,1272,1273,2000,2010,2020,2100,2200,2300,2310,2320,2400,2500,2510,2520,2530,2600,2700,2800,2810,2900,2950,2951,2952,2953 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-Tutorial-6.03 | 1/1/1 | None (tagged only) | n/a (trunk) | 100,1230,1272 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-Tutorial-6.03 | 1/1/3 | 1230 | 2700 (VL-av-01) | 100 | 1 | F8:25:51:CB:8C:76 | Moved to 2700 on 9 Oct (added on site, not in the cutover file).
switch-200V-Tutorial-6.03 | 1/1/9 | 1230 | 2700 (VL-av-01) | 100 | 1 | 01d.560a.dfc0 | Moved to 2700 on 9 Oct (added on site, not in the cutover file). MAC 01d.560a.dfc0 = 00:1D:56:0A:DF:C0, the AV Switcher on the Not found tab (master row 769)
switch-200V-Tutorial-6.03 | 1/1/10 | None (tagged only) | n/a (trunk) | 100 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-Tutorial-6.03 | 1/1/11 | 100 | 2010 (VL-wifimgmt-01) |  | 0
switch-200V-Tutorial-6.03 | 1/1/12 | None (tagged only) | n/a (trunk) | 100 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-stack-lv3 | 1/1/12 | 100 (management) | 2010 (VL-wifimgmt-01) | 1212,1213,1230,1240,1250,1271,1272,1273 | 0
switch-200V-stack-lv3 | 1/1/34 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 1/1/48 | 100 (management) | 2010 (VL-wifimgmt-01) |  | 1 | 00:09:F5:32:DB:49
switch-200V-stack-lv3 | 2/1/14 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 2/1/16 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:69:BE | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 2/1/17 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V3J5, device 20:7B:D2:30:98:F3 (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv3 | 2/1/24 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 2/1/27 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 2/1/29 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6E:9B | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 2/1/34 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 3/1/3 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 4C:C5:D9:D0:8D:2A | Moved 9 Oct (Review tab change).
switch-200V-stack-lv3 | 3/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/10 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/13 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/15 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/16 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/19 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/20 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct (live device seen 10 Oct).
switch-200V-stack-lv3 | 3/1/27 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 3/1/28 | 230 (Library) | 2530 (VL-library-01) - check |  | 0
switch-200V-stack-lv3 | 3/1/29 | 230 (Library) | 2530 (VL-library-01) - check |  | 1 | D8:3A:DD:C6:37:A8 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv3 | 3/1/31 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | D0:C1:B5:21:B3:20 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv3 | 3/1/33 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 1C:1A:DF:C2:45:23 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv3 | 3/1/43 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 1C:1A:DF:C2:45:39 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv3 | 3/1/44 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3B20 (moved 5 Oct)
switch-200V-stack-lv3 | 3/1/45 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3B21 (moved 5 Oct)
switch-200V-stack-lv3 | 3/1/46 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3B22 (moved 5 Oct)
switch-200V-stack-lv3 | 3/1/47 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3B23 (moved 5 Oct)
switch-200V-stack-lv3 | 3/1/48 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3B24 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/1 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C1 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 4/1/5 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C5 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/6 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C6 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/7 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C7 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/8 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C8 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/9 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C9 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/10 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C10 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/11 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C11 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/12 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 1 | 1C:1A:DF:C2:4C:A0 | Pilot staff outlet 200V3C12 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/13 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C13 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/14 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C14 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/15 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C15 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/16 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C16 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/17 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C17 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/18 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C18 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/19 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C19 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/20 | 2100 (VL-staff-wired-01) | Already on 2100 |  | 0 |  | Pilot staff outlet 200V3C20 (moved 5 Oct)
switch-200V-stack-lv3 | 4/1/23 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 4/1/24 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 4/1/25 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 4/1/26 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 4/1/27 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv3 | 4/1/28 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | AC:B4:80:F1:61:85 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv3 | 4/1/29 | 230 (Library) | 2530 (VL-library-01) - check |  | 1 | 2C:CF:67:A6:4B:DE | Moved 9 Oct (Review tab change).
switch-200V-stack-lv3 | 4/1/41 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6C:A8 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 4/1/43 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V3G16, device 20:7B:D2:30:98:D6 (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv3 | 4/1/45 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 4/1/46 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6D:30 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 5/1/4 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/5 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/6 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/7 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/11 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V3H2, device 20:7B:D2:30:99:09 (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv3 | 5/1/13 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/15 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/18 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6E:B0 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 5/1/20 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/23 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V3I8, device 20:7B:D2:30:98:AF (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv3 | 5/1/24 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6E:3C | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 5/1/26 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6F:04 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 5/1/29 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V3I16, device 20:7B:D2:30:98:D2 (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv3 | 5/1/32 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/40 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V3H14, device 20:7B:D2:30:98:B1 (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv3 | 5/1/43 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv3 | 5/1/45 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6F:00 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv3 | 5/1/47 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V3H21, device 20:7B:D2:30:99:29 (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv4 | 1/1/8 | 100 (management) | 2010 (VL-wifimgmt-01) | 1272,1273,2300,2310,2311,2320,2321 | 0
switch-200V-stack-lv4 | 1/1/14 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6E:06 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 1/1/15 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V4H22, device 20:7B:D2:30:98:FD (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv4 | 1/1/17 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 1/1/21 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V4I10, device 20:7B:D2:30:98:EF (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv4 | 1/1/28 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6A:29 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 1/1/30 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V4J4, device 20:7B:D2:30:98:DB (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv4 | 1/1/32 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 1/1/34 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V4J14, device 20:7B:D2:30:99:0E (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv4 | 1/1/48 | 100 (management) | 2010 (VL-wifimgmt-01) |  | 1 | 00:09:F5:32:D9:F7
switch-200V-stack-lv4 | 2/1/8 | 1212 (200V_IPcam) | 2600 (VL-cctv-01) |  | 0
switch-200V-stack-lv4 | 2/1/18 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 2/1/20 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 2/1/21 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:70:1E | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 3/1/1 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct (live device seen 10 Oct).
switch-200V-stack-lv4 | 3/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | D4:A2:CD:E4:99:ED | Moved 9 Oct (Review tab change).
switch-200V-stack-lv4 | 3/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/13 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/14 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/19 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/20 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/21 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/22 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/27 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/28 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | A0:4A:5E:E7:D5:71 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv4 | 3/1/29 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/30 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/35 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/37 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/39 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/42 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/43 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/45 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/47 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 3/1/48 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv4 | 4/1/1 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/2 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/4 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V4F5, device 20:7B:D2:30:98:DF (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv4 | 4/1/6 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6D:56 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 4/1/7 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/10 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/16 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/17 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/19 | 1272 (200V_av) | 2700 (VL-av-01) |  | 1 | 38:4B:76:E0:B0:B1 | Moved to 2700 on 10 Oct (live device seen 10 Oct).
switch-200V-stack-lv4 | 4/1/26 | 1230 (200V_av) | 2100 (VL-staff-wired-01) |  | 0 |  | Moved to 2100 on 10 Oct. Outlet 200V4H2, device 20:7B:D2:30:98:C2 (Dycom patching sheet 2025-07-30).
switch-200V-stack-lv4 | 4/1/27 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/28 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/29 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/30 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | F8:25:51:CC:2C:76 | Moved to 2700 on 10 Oct (Review item 49).
switch-200V-stack-lv4 | 4/1/31 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/32 | 1272 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/38 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/39 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 4/1/44 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/1 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/2 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/5 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/7 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:69:32 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 5/1/12 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6C:8C | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 5/1/14 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/16 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/19 | 1272 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/21 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6D:DF | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 5/1/24 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/26 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/29 | 1230 (200V_av) | 2700 (VL-av-01) |  | 1 | D8:43:AE:B1:6F:10 | Moved to 2700 on 9 Oct (unlisted AV device).
switch-200V-stack-lv4 | 5/1/35 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/38 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/40 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/43 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv4 | 5/1/47 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 1/1/1 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1230,1250,1271,1272,1273 | 0
switch-200V-stack-lv6 | 1/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1230,1250,1271,1272,1273 | 0
switch-200V-stack-lv6 | 1/1/3 | None (tagged only) | n/a (trunk) | 100,230,1212,1213,1230,1240,1250,1271,1272,1273 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-stack-lv6 | 1/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1230,1250,1271,1272,1273 | 0
switch-200V-stack-lv6 | 1/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1230,1250,1271,1272,1273 | 0
switch-200V-stack-lv6 | 1/1/6 | None (tagged only) | n/a (trunk) | 1230,1250,1271,1272,1273 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-stack-lv6 | 1/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1230,1250,1271,1272,1273 | 0
switch-200V-stack-lv6 | 1/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/12 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/30 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/31 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 1 | 1C:1A:DF:C2:44:7A | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 1/1/32 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/33 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/34 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/35 | 100 (management) | 2010 (VL-wifimgmt-01) | 1212,1213,1230,1240,1250,1271,1272,1273 | 0
switch-200V-stack-lv6 | 1/1/36 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/41 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/42 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/43 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/44 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/45 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272 | 0
switch-200V-stack-lv6 | 1/1/46 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1272,1273 | 0
switch-200V-stack-lv6 | 1/1/47 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) | 1273 | 0
switch-200V-stack-lv6 | 1/1/48 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/6 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/8 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/10 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/12 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/13 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 2/1/46 | None (tagged only) | n/a (trunk) | 100,230,1212,1213,1230,1240,1250,1271,1272,1273 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-stack-lv6 | 2/1/47 | 2010 (VL-wifimgmt-01) | Already on 2010 |  | 0
switch-200V-stack-lv6 | 2/1/48 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/1 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | A0:4A:5E:E7:D3:D5 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 3/1/2 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 3/1/3 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/6 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/8 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/10 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/21 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/22 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 3/1/23 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 4/1/1 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 1C:1A:DF:C2:45:96 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 4/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 4/1/3 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 4/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 4/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/3 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/6 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/8 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/10 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/12 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/13 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/14 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/15 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/16 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/17 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/18 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/19 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/20 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/21 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/22 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/23 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/24 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/25 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/26 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/27 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/28 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/29 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/30 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 1C:1A:DF:C0:98:B8 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 5/1/31 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/32 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/33 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/35 | 100 (management) | 2010 (VL-wifimgmt-01) | 230,1212,1213,1230,1250,1271,1272,1273 | 0
switch-200V-stack-lv6 | 5/1/36 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/37 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 5/1/39 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/40 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/41 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/43 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/44 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/45 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/46 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/47 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 5/1/48 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 1C:1A:DF:C2:4E:3C | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 6/1/1 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/3 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/4 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/5 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/6 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/7 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/8 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/9 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/10 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/11 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/12 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/13 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/14 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/15 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/16 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 1C:1A:DF:C0:31:0F | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 6/1/17 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/18 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/19 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 6/1/21 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/22 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 1C:1A:DF:C2:51:31 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 6/1/23 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 6/1/25 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/29 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 6/1/30 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/31 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 1 | 48:21:0B:56:AE:44 | Moved 9 Oct (Review tab change).
switch-200V-stack-lv6 | 6/1/32 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/33 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/36 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/37 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/42 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/43 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/44 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/47 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 6/1/48 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/1 | None (tagged only) | n/a (trunk) | 100,230,1212,1213,1230,1240,1250,1271,1272,1273 | 0 |  | Trunk/uplink: tagged VLANs only
switch-200V-stack-lv6 | 7/1/2 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/6 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/7 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 7/1/12 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/13 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/15 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/16 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/18 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/20 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/21 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/25 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/26 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/29 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/36 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/37 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/38 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/39 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/41 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/42 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/43 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 7/1/45 | 1230 (200V_av) | 2700 (VL-av-01) |  | 0
switch-200V-stack-lv6 | 7/1/46 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/47 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0
switch-200V-stack-lv6 | 7/1/48 | 1240 (200V_staff) | 2100 (VL-staff-wired-01) |  | 0

## Not found
Master row | Type | Device | MAC | Old VLAN | New VLAN | Reason
475 | AP | r650-39-4d-10 | C8:A6:08:39:4D:10 | 100 (management) | 2010 (VL-wifimgmt-01) | MAC not in 200V tab
769 | AV | AV Switcher | 00:1D:56:0A:DF:C0 | Unknown | 2700 (VL-av-01) | MAC not in 200V tab
779 | AV | AV Switcher | 00-1D-56-0A-B4-AB | Unknown | 2700 (VL-av-01) | MAC not in 200V tab
1121 | AV | Projector | F8:25:51:72:A4:52 | Unknown | 2700 (VL-av-01) | MAC not in 200V tab
1134 | AV | Projector | F8:25:51:CB:8C:94 | Unknown | 2700 (VL-av-01) | MAC not in 200V tab
1145 | AV | Projector | F8:25:51:CC:0F:C6 | Unknown | 2700 (VL-av-01) | MAC not in 200V tab

## Summary
Source | Devices master list, Devices tab, Location = 200V
Devices with a port | 392
Done (pilot) | 39
Done (9 Oct cutover) | 353
To do | 0
Port matched from 200V tab (check) | 14
Not found on any switch | 6
Total 200V devices | 398
Switch | Devices
switch-200V-LT2-1 | 16
switch-200V-Tutorial-6.03 | 6
switch-200V-stack-lv3 | 93
switch-200V-stack-lv4 | 110
switch-200V-stack-lv6 | 167
Legend
Green row | Moved in the 5 October pilot or the 9 October cutover (yellow rows were also moved)
Yellow row | Master list lookup failed; switch and port taken from the 200V tab by MAC
Ports with a VLAN but no device listed | 361
MAC seen on port (orange) | 45
No MAC seen | 316
Pilot staff outlets (green) | 22
Trunk / uplink ports (grey) | 12
Orange row | Ports without device tab: a MAC was seen on the port but no device is listed
Review items | 112
Decided | 51
Open | 61